## OBS
WBS ID | DELIBERABLES | RESPONSIBLE ORG.
1.1 | Project Management | Project Management Division
1.2 | Regulatory & Environmental | Regulatory Affairs / Environmental Services
1.3 | Prototype & Design | Transmission & Distribution
1.4 | Material Procurement | Supply Chain Management
1.5 | Site Easement | Transmission & Distribution
1.6 | Cable Installation | Substation Construction & Maintenance
1.7 | Commissioning & Closeout | Substation Construction & Maintenance

## Time and Cost Estimation
Work Packages | Time Estimate (days) | Cost (Micro) | Cost (Mid) | Cost (Macro)
1. Project Management | - | - | - | 20000
1.1 Project charter | 10 | 10000 | 20000 | -
1.2 Scope of Work | 20 | 10000 | - | -
2. Regulatory & Environmental | - | - | - | 125000
2.1 Regulatory Permits | 20 | 50000 | - | -
2.2 Environmental Compliance | 21 | 75000 | - | -
3. Prototypes and Designs | - | - | - | 870000
3.1 Corridor Identification | - | - | 60000 | -
3.1.1 Route alignment | 42 | 30000 | - | -
3.1.2 Seismic design & load studies | 42 | 30000 | - | -
3.2 Civil & Structural Design | - | - | 500000 | -
3.2.1 Footing design | 48 | 200000 | - | -
3.2.2 Tower structure design | 48 | 300000 | - | -
3.3 Electrical & Protection Design | - | - | 310000 | -
3.3.1 Cable sizing & specification | 28 | 40000 | - | -
3.3.2 Grounding system design | 48 | 150000 | - | -
3.3.3 Relay/protection coordination | 42 | 120000 | - | -
4. Materials Procurement | - | - | 5500000 | 5500000
4.1 500kV cable procurement | 100 | 3000000 | - | -
4.2 Tower Structural Materials | 84 | 2500000 | - | -
5. Site Easement | - | - | - | 5050000
5.1 Site Preparation | - | - | 1350000 | -
5.1.1 Surveying & staking | 56 | 150000 | - | -
5.1.2 Clearing & grading | 84 | 1200000 | - | -
5.2 Tower Construction | - | - | 3700000 | -
5.2.2 Tower structure construction | 84 | 1200000 | - | -
5.2.3 Tower structure Assembly | 45 | 2500000 | - | -
6. Cable Installation | - | - | - | 3300000
6.1 Cable Pulling | - | - | 3300000 | -
6.1.1 Cable drum delivery & setup | 70 | 100000 | - | -
6.1.2 Cable pulling operations | 105 | 2500000 | - | -
6.1.3 Cable Splicing | 70 | 600000 | - | -
6.1.4 Cable Testing | 30 | 100000 | - | -
7. Commissioning & Closeout | - | - | - | 450000
7.1 System Energization | - | - | 250000 | -
7.1.1 Pre-energization checklist | 28 | 150000 | - | -
7.1.2 Energization testing | 28 | 100000 | - | -
7.2 Project Closeout | - | - | 200000 | -
7.2.1 As-built documentation | 28 | 150000 | - | -
7.2.2 Lessons learned Report | 14 | 50000 | - | -
Totals (concurrency not factored) | 1195 |  |  | 15315000

## Responsability Matrix
WBS ID | Deliverable | Project Manager | Engineering Lead | Procurement Lead | Construction Lead | Regulatory Affairs | Community Relations | LEGEND
1 | Project Management | R | I | I | I | S | C | R | Responsible | Directly Doing work
2 | Regulatory & Environmental | I | C |  | C | R | S | S | Support | Supporting the work
3 | Prototype & Designs | I | R | C | C | I |  | C | Consult | Consulting
4 | Materials Procurement | I | C | R | C | C |  | I | Informed | Just gets informed
5 | Site Easement | I | S | R | S | C
6 | Cable Installation | I | S | I | R | C
7 | Commissioning & Closeout | C | R |  | R | C | I

## Network Diagram
LEGEND |  |  | Total Slack |  | 1.1=1509, 1.2=1509, 2.1=1510, 2.2=1509, 3.1.1=1509, 3.1.2=1515, 3.2.1=1515, 3.2.2=1515, 3.3.1=1529, 3.3.2=1509, 3.3.3=1515, 4.1=1509, 4.2=1509, 5.1.1= 1537, 5.1.2=1509, 5.2.2=1509, 5.2.3= 1548, 6.1.1=1509,
ES | ID | EF | Critical Paths |  | 1.1->1.2->2.2->3.1.1->3.3.2->4.1->4.2->5.1.2->6.1.1->6.1.2->7.1.1->7.1.2->7.1.2->7.2.1->7.2.2
SL | DESCRIPTION |  |  |  | 1.1->1.2->2.2->3.1.1->3.3.2->4.1->4.2->5.2.2->6.1.1->6.1.2->7.1.1->7.1.2->7.1.2->7.2.1->7.2.2
LS | DUR | LF | Sensitivity |  | High
|  |  | Total Project Slack |  | 1509
[12 empty] | 93 | 3.1.2 | 135
[12 empty] | 1515 | Seismic Design
[12 empty] | 1608 | 42 | 1650
[12 empty] | 93 | 3.2.1 | 135 | [6 empty] | 325 | 5.1.1 | 381
[12 empty] | 1515 | Footing Design | [7 empty] | 1537 | Survey & staking
[12 empty] | 1608 | 42 | 1650 | [6 empty] | 1862 | 56 | 1918 |  |  |  | 479 | 6.1.2 | 584
[27 empty] | 1509 | Cable pulling
[6 empty] | 30 | 2.1 | 50 |  |  |  | 93 | 3.2.2 | 135 | [6 empty] | 325 | 5.1.2 | 409 |  |  |  | 1988 | 105 | 2093
[6 empty] | 1510 | Regulatory permits |  |  |  |  | 1515 | Tower Structure D. | [7 empty] | 1509 | Clearing and grading
[6 empty] | 1540 | 20 | 1560 |  |  |  | 1608 | 42 | 1650 | [6 empty] | 1834 | 84 | 1918 |  |  |  | 479 | 6.1.3 | 549
0 | 1.1 | 10 | 10 | 1.2 | 30 |  |  |  | 51 | 3.1.1 | 93 |  |  |  | 141 | 4.1 | 241 | 241 | 4.2 | 325 |  |  |  | 409 | 6.1.1 | 479 | 1544 | Cable splicing |  | 584 | 7.1.1 | 612 | 612 | 7.1.2 | 640 | 640 | 7.2.1 | 668 | 668 | 7.2.2 | 682
1509 | Project charter |  | 1509 | Scope of work |  |  |  |  | 1509 | Route alignment |  | 93 | 3.3.1 | 121 | 1509 | Cable procurement |  | 1509 | Tower Structure |  |  |  |  | 1509 | Cable drum delivery |  | 2023 | 70 | 2093 | 1509 | Pre-energization |  | 1509 | Energization |  | 1509 | As-built |  | 1509 | Lessons learn
1509 | 10 | 1519 | 1519 | 20 | 1539 |  |  |  | 1560 | 42 | 1602 | 1529 | Cable Sizing |  | 1650 | 100 | 1750 | 1750 | 84 | 1834 | 325 | 5.2.2 | 409 | 1918 | 70 | 1988 |  |  |  | 2093 | 28 | 2121 | 2121 | 28 | 2149 | 2149 | 28 | 2177 | 2177 | 14 | 2191
[6 empty] | 30 | 2.2 | 51 |  |  |  | 1622 | 28 | 1650 | [6 empty] | 1509 | Tower construction |  |  |  |  | 479 | 6.1.4 | 549
[6 empty] | 1509 | Environmental compliance | [13 empty] | 1834 | 84 | 1918 |  |  |  | 1544 | Cable testing
[6 empty] | 1539 | 21 | 1560 |  |  |  | 93 | 3.3.2 | 141 | [12 empty] | 2023 | 70 | 2093
[12 empty] | 1509 | Grounding Design | [7 empty] | 325 | 5.2.3 | 370
[12 empty] | 1602 | 48 | 1650 | [6 empty] | 1548 | Tower assembly
[21 empty] | 1873 | 45 | 1918
[12 empty] | 93 | 3.3.3 | 135
[12 empty] | 1515 | Relay coordinatIon
[12 empty] | 1608 | 42 | 1650

## Resources
ID | JOB PACKAGES | Time estimate (Days) | Cost (Micro) | RESOURCES | Project Duration (Days) | 2191
1.1 | Project charter | 10 | 10000 | Project Manager (PM)
1.2 | Scope of Work | 20 | 10000 | Project Manager (PM)
2.1 | Regulatory Permits | 20 | 50000 | Regulatory Specialist (RS) / Compliance Specialist (CS)
2.2 | Environmental Compliance | 21 | 75000 | Compliance Specialist (CS)
3.1.1 | Route alignment | 42 | 30000 | Geotechnical Engineer (GE)
3.1.2 | Seismic design & load studies | 42 | 30000 | Geotechnical Engineer (GE) / Structural Engineer (SE)
3.2.1 | Footing design | 48 | 200000 | Structural Engineer (SE)
3.2.2 | Tower structure design | 48 | 300000 | Structural Engineer (SE)
3.3.1 | Cable sizing & specification | 28 | 40000 | Electrical Engineer (EE)
3.3.2 | Grounding system design | 48 | 150000 | Electrical Engineer (EE)
3.3.3 | Relay/protection coordination | 42 | 120000 | Logistics Coordinator (LC)
4.1 | 500kV cable procurement | 100 | 3000000 | Logistics Coordinator (LC)
4.2 | Tower Structural Materials | 84 | 2500000 | Structural Engineer (SE)
5.1.1 | Surveying & staking | 56 | 150000 | Geotechnical Engineer (GE)
5.1.2 | Clearing & grading | 84 | 1200000 | Construction Manager (CM)
5.2.2 | Tower structure construction | 84 | 1200000 | Construction Manager (CM)
5.2.3 | Tower structure Assembly | 45 | 2500000 | Construction Manager (CM)
6.1.1 | Cable drum delivery & setup | 70 | 100000 | Logistics Coordinator (LC)
6.1.2 | Cable pulling operations | 105 | 2500000 | Construction Manager (CM)
6.1.3 | Cable Splicing | 70 | 600000 | Cable Splicing Specialist (CS) / Electrical Engineer (EE)
6.1.4 | Cable Testing | 30 | 100000 | QA-QC Engineer (QA)
7.1.1 | Pre-energization checklist | 28 | 150000 | QA-QC Engineer (QA)
7.1.2 | Energization testing | 28 | 100000 | QA-QC Engineer (QA) / Electrical Engineer (EE)
7.2.1 | As-built documentation | 28 | 150000 | Project Manager (PM) / Structural Engineer (SE) / Electrical Engineer (EE)
7.2.2 | Lessons learned Report | 14 | 50000 | Project Manager (PM)

## Loading Schedule
LEGEND |  |  |  | Total Slack |  | 1324
ES | ID | EF |  | Critical Path(s)
SL | DESCRIPTION / RESOURCE(s) |  |  | Sensitivity |  | Medium
LS | DUR | LF |  | Total Project Slack |  | 1324
[20 empty] | 113 | 3.1.2 | 155
[20 empty] | 1366 | Seismic Design (GE) (SC) | [30 empty] | 664 | 6.1.2 | 769
[20 empty] | 1479 | 42 | 1521 | [29 empty] | 1324 | Cable pulling (CM)
[52 empty] | 1988 | 105 | 2093
[20 empty] | 113 | 3.2.1 | 155 | [13 empty] | 381 | 5.1.1 | 437
[20 empty] | 1324 | Footing Design (SE) | [14 empty] | 1481 | Survey & staking (GE) | [14 empty] | 664 | 6.1.3 | 734
0 | 1.1 | 10 |  | 10 | 1.2 | 30 |  | 30 | 2.2 | 51 |  | 51 | 2.1 | 71 |  | 71 | 3.1.1 | 113 |  | 1437 | 42 | 1479 | [5 empty] | 197 | 4.1 | 297 |  | 297 | 4.2 | 381 |  | 1862 | 56 | 1918 | [9 empty] | 594 | 6.1.1 | 664 |  | 1359 | Cable splicing (CS) (EE) |  |  | 769 | 7.1.1 | 797 | 797 | 7.1.2 | 825 | 825 | 7.2.1 | 853 | 853 | 7.2.2 | 867
1324 | Project charter (PM) |  |  | 1324 | Scope of work (PM) |  |  | 1324 | Environmental compliance (CS) |  |  | 1324 | Regulatory permits (RS) (CS) |  |  | 1324 | Route alignment (GE) | [6 empty] | 155 | 3.2.2 | 197 |  | 1324 | Cable procurement (EE) |  |  | 1324 | Tower Structure (SE) | [14 empty] | 1324 | Cable drum delivery (LC) |  |  | 2023 | 70 | 2093 |  | 1324 | Pre-energization (QA) |  | 1324 | Energization (QA) |  | 1324 | As-built (PM) (SE) (EE) |  | 1324 | Lessons learn (PM)
1324 | 10 | 1334 |  | 1334 | 20 | 1354 |  | 1354 | 21 | 1375 |  | 1375 | 20 | 1395 |  | 1395 | 42 | 1437 |  | 113 | 3.3.3 | 155 |  | 1324 | Tower Structure D. (SE) |  |  | 1521 | 100 | 1621 |  | 1621 | 84 | 1705 |  | 381 | 5.1.2 | 465 |  | 465 | 5.2.2 | 549 |  | 549 | 5.2.3 | 594 |  | 1918 | 70 | 1988 | [5 empty] | 2093 | 28 | 2121 | 2121 | 28 | 2149 | 2149 | 28 | 2177 | 2177 | 14 | 2191
[20 empty] | 1338 | Relay coordinatIon (LC) |  |  | 1479 | 42 | 1521 | [9 empty] | 1324 | Clearing and grading (CM) |  |  | 1324 | Tower construction (CM) |  |  | 1324 | Tower assembly (CM) | [6 empty] | 664 | 6.1.4 | 734
[20 empty] | 1451 | 42 | 1493 | [13 empty] | 1705 | 84 | 1789 |  | 1789 | 84 | 1873 |  | 1873 | 45 | 1918 | [5 empty] | 1359 | Cable testing (QA)
[52 empty] | 2023 | 70 | 2093
[20 empty] | 113 | 3.3.2 | 161 |  | 161 | 3.3.1 | 189
[20 empty] | 1332 | Grounding Design (EE) |  |  | 1332 | Cable Sizing (EE)
[20 empty] | 1445 | 48 | 1493 |  | 1493 | 28 | 1521
Loading Schedule (Weekdays only)
Months | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5 | 9 | 9.1 | 10 | 10.5 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 34.5 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 41.5 | 42 | 43 | 44 | 44.5
PM | 1.1 | 1.2 | 1.2 | [50 empty] | 7.2.1 | 7.2.1 | 7.2.2
CS |  |  |  | 2.2 | 2.2 | [38 empty] | 6.1.3 | 6.1.3 | 6.1.3 | 6.1.3
RS | [5 empty] | 2.1 | 2.1
GE | [7 empty] | 3.1.1 | 3.1.1 | 3.1.1 | 3.1.1 | 3.1.2 | 3.1.2 | 3.1.2 | 3.1.2 | [14 empty] | 5.1.1 | 5.1.1 | 5.1.1
SC | [11 empty] | 3.1.2 | 3.1.2 | 3.1.2 | 3.1.2
SE | [11 empty] | 3.2.1 | 3.2.1 | 3.2.1 | 3.2.1 | 3.2.2 | 3.2.2 | 3.2.2 | 3.2.2 | 3.2.2 | [33 empty] | 7.2.1 | 7.2.1
LC | [11 empty] | 3.3.3 | 3.3.3 | 3.3.3 | 3.3.3 |  | 3.3.1 | 3.3.1 | 3.3.1 |  | 4.1 | 4.1 | 4.1 | 4.1 | 4.1 | 4.2 | 4.2 | 4.2 | 4.2 | [10 empty] | 6.1.1 | 6.1.1 | 6.1.1 | 6.1.1
EE | [11 empty] | 3.3.2 | 3.3.2 | 3.3.2 | 3.3.2 | 3.3.2 | 3.3.1 | 3.3.1 | 3.3.1 | [24 empty] | 6.1.3 | 6.1.3 | 6.1.3 | 6.1.3 | [6 empty] | 7.2.1 | 7.2.1
CM | [29 empty] | 5.1.2 | 5.1.2 | 5.1.2 | 5.1.2 | 5.2.2 | 5.2.2 | 5.2.2 | 5.2.2 | 5.2.3 | 5.2.3 | 6.1.1 | 6.1.1 | 6.1.1 | 6.1.1 | 6.1.2 | 6.1.2 | 6.1.2 | 6.1.2 | 6.1.2 | 6.1.2
QA | [43 empty] | 6.1.4 | 6.1.4 | 6.1.4 | 6.1.4 |  |  | 7.1.1 | 7.1.1 | 7.1.2 | 7.1.2

## Time Phased Budget
Project Start Date: 01/05/2026 |  |  |  | Months -->
ID | DUR(Weeks) Weekdays Only | Job Package | Budget ($000) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | Total ($000)
1.1 | 2 | Project charter | 10 | Months --> 1: 10 | 10
1.2 | 4 | Scope of Work | 10 | Months --> 1: 5; Months --> 2: 5 | 10
2.2 | 4.2 | Environmental Compliance | 75 | Months --> 2: 37; Months --> 3: 38 | 75
2.1 | 4 | Regulatory Permits | 50 | Months --> 3: 25; Months --> 4: 25 | 50
3.1.1 | 8.4 | Route alignment | 30 | Months --> 4: 10; Months --> 5: 15; Months --> 6: 5 | 30
3.1.2 | 8.4 | Seismic design & load studies | 30 | Months --> 6: 15; Months --> 7: 6; Months --> 8: 9 | 30
3.2.1 | 5.6 | Footing design | 200 | Months --> 6: 53; Months --> 7: 55; Months --> 8: 92 | 200
3.3.3 | 16.8 | Relay/protection coordination | 120 | Months --> 6: 51; Months --> 7: 66; Months --> 8: 3 | 120
3.3.2 | 9.6 | Grounding system design | 150 | Months --> 6: 19; Months --> 7: 66; Months --> 8: 65 | 150
3.2.2 | 20 | Tower structure design | 300 | Months --> 8: 105; Months --> 9: 63; Months --> 10: 132 | 300
3.3.1 | 9.6 | Cable sizing & specification | 40 | Months --> 9: 17; Months --> 10: 23 | 40
4.1 | 11.2 | 500kV cable procurement | 3000 | Months --> 11: 360; Months --> 12: 690; Months --> 13: 630; Months --> 14: 660; Months --> 15: 660 | 3000
4.2 | 16.8 | Tower Structural Materials | 2500 | Months --> 16: 148; Months --> 17: 655; Months --> 18: 625; Months --> 19: 685; Months --> 20: 387 | 2500
5.1.1 | 9.6 | Surveying & staking | 150 | Months --> 21: 35; Months --> 22: 59; Months --> 23: 56 | 150
5.1.2 | 8.4 | Clearing & grading | 1200 | Months --> 21: 229; Months --> 22: 300; Months --> 23: 314; Months --> 24: 357 | 1200
5.2.2 | 9 | Tower structure construction | 1200 | Months --> 25: 104; Months --> 26: 286; Months --> 27: 329; Months --> 28: 324; Months --> 29: 157 | 1200
5.2.3 | 21 | Tower structure Assembly | 2500 | Months --> 29: 1278; Months --> 30: 1222 | 2500
6.1.1 | 16.8 | Cable drum delivery & setup | 100 | Months --> 31: 14; Months --> 32: 33; Months --> 33: 30; Months --> 34: 23 | 100
6.1.2 | 14 | Cable pulling operations | 2500 | Months --> 34: 96; Months --> 35: 548; Months --> 36: 524; Months --> 37: 500; Months --> 38: 524; Months --> 39: 308 | 2500
6.1.3 | 14 | Cable Splicing | 600 | Months --> 34: 77; Months --> 35: 189; Months --> 36: 189; Months --> 37: 145 | 600
6.1.4 | 6 | Cable Testing | 100 | Months --> 34: 13; Months --> 35: 48; Months --> 36: 25; Months --> 37: 14 | 100
7.1.1 | 5.6 | Pre-energization checklist | 150 | Months --> 40: 102; Months --> 41: 48 | 150
7.1.2 | 5.6 | Energization testing | 100 | Months --> 41: 43; Months --> 42: 57 | 100
7.2.1 | 5.6 | As-built documentation | 150 | Months --> 43: 27; Months --> 44: 123 | 150
7.2.2 | 2.8 | Lessons learned Report | 50 | Months --> 44: 50 | 50
|  | Total |  | 15 | 42 | 63 | 35 | 15 | 143 | 193 | 274 | 80 | 155 | 360 | 690 | 630 | 660 | 660 | 148 | 655 | 625 | 685 | 387 | 264 | 359 | 370 | 357 | 104 | 286 | 329 | 324 | 1435 | 1222 | 14 | 33 | 30 | 209 | 785 | 738 | 659 | 524 | 308 | 102 | 91 | 57 | 27 | 173 | 15315
|  | Cumulative | 15315 | 15 | 57 | 120 | 155 | 170 | 313 | 506 | 780 | 860 | 1015 | 1375 | 2065 | 2695 | 3355 | 4015 | 4163 | 4818 | 5443 | 6128 | 6515 | 6779 | 7138 | 7508 | 7865 | 7969 | 8255 | 8584 | 8908 | 10343 | 11565 | 11579 | 11612 | 11642 | 11851 | 12636 | 13374 | 14033 | 14557 | 14865 | 14967 | 15058 | 15115 | 15142 | 15315

## Crashing
Total Indirect cost | 1104000
Saving per Unit Reduced | 1200
Duration | 2191
Total Direct Cost | 15315000
Actual cost | 16419000
Activity | Crash Cost | Maximum Crash Time | Normal Time | Normal Cost | Indirect Cost
Project charter | 2000 | 2 | 10 | 10000 | 2000
Scope of Work | 2000 | 4 | 20 | 10000 | 2000
Regulatory Permits | 15000 | 5 | 20 | 50000 | 10000
Environmental Compliance | 22500 | 5 | 21 | 75000 | 10000
Route alignment | 10000 | 10 | 42 | 30000 | 10000
Seismic design & load studies | 10000 | 10 | 42 | 30000 | 10000
Footing design | 70000 | 12 | 48 | 200000 | 50000
Tower structure design | 100000 | 12 | 48 | 300000 | 75000
Cable sizing & specification | 12000 | 7 | 28 | 40000 | 10000
Grounding system design | 45000 | 12 | 48 | 150000 | 50000
Relay/protection coordination | 30000 | 10 | 42 | 120000 | 50000
500kV cable procurement | 1100000 | 35 | 100 | 3000000 | 100000
Tower Structural Materials | 1000000 | 24 | 84 | 2500000 | 100000
Surveying & staking | 40000 | 16 | 56 | 150000 | 50000
Clearing & grading | 450000 | 24 | 84 | 1200000 | 100000
Tower structure construction | 450000 | 24 | 84 | 1200000 | 100000
Tower structure Assembly | 1120000 | 15 | 45 | 2500000 | 100000
Cable drum delivery & setup | 22000 | 20 | 70 | 100000 | 25000
Cable pulling operations | 1120000 | 40 | 105 | 2500000 | 100000
Cable Splicing | 240000 | 20 | 70 | 600000 | 75000
Cable Testing | 30000 | 7 | 30 | 100000 | 20000
Pre-energization checklist | 20000 | 10 | 28 | 150000 | 20000
Energization testing | 25000 | 10 | 28 | 100000 | 15000
As-built documentation | 15000 | 13 | 28 | 150000 | 10000
Lessons learned Report | 5000 | 4 | 14 | 50000 | 10000
[16 empty] | 113 | 3.1.2 | 155
[16 empty] | 1366 | Seismic Design (GE) (SC) | [22 empty] | 664 | 6.1.2 | 769
[16 empty] | 1479 | 42 | 1521 | [21 empty] | 1324 | Cable pulling (CM)
[40 empty] | 1988 | 105 | 2093
[16 empty] | 113 | 3.2.1 | 155 | [9 empty] | 381 | 5.1.1 | 437
[16 empty] | 1324 | Footing Design (SE) | [10 empty] | 1481 | Survey & staking (GE) | [10 empty] | 664 | 6.1.3 | 734
0 | 1.1 | 10 |  | 10 | 1.2 | 30 | 30 | 2.2 | 51 | 51 | 2.1 | 71 | 71 | 3.1.1 | 113 | 1437 | 42 | 1479 |  |  |  | 197 | 4.1 | 297 | 297 | 4.2 | 381 | 1862 | 56 | 1918 | [6 empty] | 594 | 6.1.1 | 664 | 1359 | Cable splicing (CS) (EE) |  | 769 | 7.1.1 | 797 | 797 | 7.1.2 | 825 | 825 | 7.2.1 | 853 | 853 | 7.2.2 | 867
1324 | Project charter (PM) |  |  | 1324 | Scope of work (PM) |  | 1324 | Environmental compliance (CS) |  | 1324 | Regulatory permits (RS) (CS) |  | 1324 | Route alignment (GE) |  |  |  |  | 155 | 3.2.2 | 197 | 1324 | Cable procurement (LC) |  | 1324 | Tower Structure (SE) | [10 empty] | 1324 | Cable drum delivery (LC) (CM) |  | 2023 | 70 | 2093 | 1324 | Pre-energization (QA) |  | 1324 | Energization (QA) |  | 1324 | As-built (PM) (SE) (EE) |  | 1324 | Lessons learn (PM)
1324 | 10 | 1334 |  | 1334 | 20 | 1354 | 1354 | 21 | 1375 | 1375 | 20 | 1395 | 1395 | 42 | 1437 | 113 | 3.3.3 | 155 | 1324 | Tower Structure D. (SE) |  | 1521 | 100 | 1621 | 1621 | 84 | 1705 | 381 | 5.1.2 | 465 | 465 | 5.2.2 | 549 | 549 | 5.2.3 | 594 | 1918 | 70 | 1988 |  |  |  | 2093 | 28 | 2121 | 2121 | 28 | 2149 | 2149 | 28 | 2177 | 2177 | 14 | 2191
[16 empty] | 1338 | Relay coordinatIon (LC) |  | 1479 | 42 | 1521 | [6 empty] | 1324 | Clearing and grading (CM) |  | 1324 | Tower construction (CM) |  | 1324 | Tower assembly (CM) |  |  |  |  | 664 | 6.1.4 | 734
[16 empty] | 1451 | 42 | 1493 | [9 empty] | 1705 | 84 | 1789 | 1789 | 84 | 1873 | 1873 | 45 | 1918 |  |  |  | 1359 | Cable testing (QA)
[40 empty] | 2023 | 70 | 2093
[16 empty] | 113 | 3.3.2 | 161 | 161 | 3.3.1 | 189
[16 empty] | 1332 | Grounding Design (EE) |  | 1332 | Cable Sizing (EE) (LC)
[16 empty] | 1445 | 48 | 1493 | 1493 | 28 | 1521
Duration | 2191 | 2189 | 2185 | 2175 | 2155 | 2142
Activity |  | Project Charter | Scope of work | Route Alignment | Cable drum delivery & setup | As-built documentation
Actual Cost | 16419000 | 16418600 | 16415800 | 16413800 | 16411800 | 16411200
Direct Cost | 15315000 | 15317000 | 15319000 | 15329000 | 15351000 | 15366000
Indirect Cost | 1104000 | 1101600 | 1096800 | 1084800 | 1060800 | 1045200
New Actual cost | 16411200
New Duration | 2142

## Status Report
Status Report: Ending Month 1
Task | % Complete | EV | AC | PV | CV | SV
1.1 | 90 | 9 | 10 | 10 | -1 | -1
1.2 | 50 | 5 | 5 | 5 | 0 | 0
Totals |  | 14 | 15 | 15 | -1 | -1
Status Report: Ending Month 2
Task | % Complete | EV | AC | PV | CV | SV
1.1 | 100 | 10 | 10 | 10 | 0 | 0
1.2 | 100 | 5 | 5 | 5 | 0 | 0
2.2 | 40 | 30 | 35 | 37 | -5 | -7
Totals |  | 45 | 50 | 52 | -5 | -7
Status Report: Ending Month 3
Task | % Complete | EV | AC | PV | CV | SV
1.1 | 100 | 10 | 10 | 10 | 0 | 0
1.2 | 100 | 5 | 5 | 5 | 0 | 0
2.2 | 80 | 60 | 73 | 75 | -13 | -15
2.1 | 50 | 25 | 27 | 25 | -2 | 0
3.1.1 | 40 | 12 | 14 | 15 | -2 | -3
Totals |  | 112 | 129 | 130 | -17 | -18
Status Report: Ending Month 4
Task | % Complete | EV | AC | PV | CV | SV
1.1 | 100 | 10 | 10 | 10 | 0 | 0
1.2 | 100 | 5 | 5 | 5 | 0 | 0
2.2 | 100 | 75 | 77 | 75 | -2 | 0
2.1 | 90 | 45 | 53 | 50 | -8 | -5
3.1.1 | 60 | 18 | 29 | 30 | -11 | -12
3.1.2 | 50 | 15 | 15 | 15 | 0 | 0
3.2.1 | 25 | 50 | 53 | 53 | -3 | -3
3.3.3 | 40 | 48 | 50 | 51 | -2 | -3
3.3.2 | 10 | 15 | 14 | 19 | 1 | -4
Totals |  | 281 | 306 | 308 | -25 | -27
Status Report: Ending Month 5
Task | % Complete | EV | AC | PV | CV | SV
1.1 | 100 | 10 | 10 | 10 | 0 | 0
1.2 | 100 | 5 | 5 | 5 | 0 | 0
2.2 | 100 | 75 | 77 | 75 | -2 | 0
2.1 | 100 | 50 | 57 | 50 | -7 | 0
3.1.1 | 100 | 30 | 42 | 30 | -12 | 0
3.1.2 | 60 | 18 | 23 | 21 | -5 | -3
3.2.1 | 40 | 80 | 82 | 108 | -2 | -28
3.3.3 | 95 | 114 | 115 | 117 | -1 | -3
3.3.2 | 35 | 52.5 | 61 | 85 | -8.5 | -32.5
Totals |  | 434.5 | 472 | 501 | -37.5 | -66.5
Performance Indexes Summary
Period |  | EV | AC | PV |  | SPI | CPI | PCI-B
1 |  | 14 | 15 | 15 |  | 0.93333 | 0.93333 | 0.00091414
2 |  | 45 | 50 | 52 |  | 0.86538 | 0.9 | 0.0029383
3 |  | 112 | 129 | 130 |  | 0.86154 | 0.86822 | 0.0073131
4 |  | 281 | 306 | 308 |  | 0.91234 | 0.9183 | 0.018348
5 |  | 434.5 | 472 | 501 |  | 0.86727 | 0.92055 | 0.028371
EACf | = | 16636.7779 |  | VACf | = | -1321.7779