## Sheet1
What Information | Target Audience | When? | Method of Commuication | Provider
Project Proposals for public comment | CPUC, City of Chino Hills, Chino Hills Residents | Prior to choosing route | Town hall meeting | Project Manager, Public Relations
Proposal Decision | City of Chino Hills, Chino Hills Residents, SoCal Edison Senior Management | After CPUC has made decision on overheading and route has been chosen | Website Bulletin, Management Meeting | Project Manager, Public Relations
Milestone Report | SoCal Edison Senior Management, Project Manager | BiMonthly | E-mail | Department Heads
Project Status Reports and Agendas | CPUC, SoCal Edison, applicable vendors | Weekly | E-mail | Project Manager
Department Statis Reports | Project Manager | Weekly | E-mail | Department Heads
Issues Report | CPUC, SoCal Edison Senior Management | Weekly | E-mail | Project Manager
Vendor Status Reports | Project Manager, Department Heads | Bi-monthly | E-mail | Vendors
Accepted Change Requests | SoCal Edison Management, CPUC, Department Heads, applicable vendors | As needed | E-mail | Project Manager
Oversight Decisions | Project Staff, SoCal Edison, Project Manager | As needed | CPUC minutes/rulings website pages | CPUC