Tehachapi Reliability Transmission Project
 Chino Hills 500kV Section - Final Report

Brian Montgomery
 Pearl Baghel
 Roberto Blanco

California State Polytechnic University, Pomona
 Course: EMT 6360 - Project Management

Fall 2025

1.	Introduction & Background	2

2.	Project Management Framework	3

2.1 Project Management Methodology	3

2.2 Project Selection Criteria/Model	3

3.	Organizational Alignment	3

3.1 Organizational & PM Structure	3

3.2 Resolving Resource Conflicts	4

3.3 Stakeholder Analysis	4

3.4 Cultural Alignment	5

3.5 Project Priority Matrix (Time–Cost–Performance Trade-offs)	5

4.	Planning & Controls	5

4.1 Work Breakdown Structure (WBS) & Coding system	5

4.2 Responsibility Assignment Matrix (RAM) & WBS/OBS Integration	6

4.3 Communication Plan	6

5.	Estimating & Scheduling	6

5.1 Cost Estimation (Macro & Micro)	7

5.2 Time Estimation	7

5.3 Network Diagram Development	7

6.	Risk & Change Management	7

6.1 Risk Management Process	8

6.2 Risk Responses & Mitigation Plans	8

6.3 Contingency Funds & Time Buffers	8

6.4 Change Control Process	8

7.	The Master Plan	9

8.	Loading Schedule Development	9

9.	Time-Phased Budget Development	9

10.	Resource Constraint	9

11.	PM's Traits and Competencies, Team Development	9

12.	Project Manager’s Traits and Competencies	10

13.	Project Management and Team Development	11

14.	Technology Challenge and Schedule Opportunity	11

14.1 Challenges we faced — and how we handled them	11

14.2 Opportunity we used — targeted crashing	12

15.	Status Reports	12

16.	Performance Metrics and Indexes	12

17.	Project Closure	13

17.1 Project closure Activities	13

17.2 Delivery Acceptance and Delivery	13

17.3 Performing a Post-Project Audit and Team Evaluation	14

17.4 Shutting down the project	14

17.5 Closing Accounts	14

17.6 Final Report	14

18.	Where is SCE on the Project Management Maturity Model	14

19.	Conclusion and Lessons Learned	15

Figures	15

Figure 1 - Map of overarching Tehachapi Project (link to source)	16

Figure 2 – Project Charter	16

Figure 3 - Project Selection/Criteria Model	17

Figure 4 - Stakeholder Analysis Table	18

Figure 5 - Project Scope of Work	19

Figure 6 - Project Priority Matrix	21

Figure 7 - Work Breakdown Structure	22

Figure 8 - Responsibility Assignment Matrix	23

Figure 9 - WBS/OBS Integration	23

Figure 10 - Communication Plan	24

Figure 11 - Cost Estimation (Macro and Micro)	25

Figure 12 - Base Network Diagram	26

Figure 13 - Risk Table	29

Figure 14 - Risk impact Matrix	30

Figure 15 - Risk Response and Mitigation Table	31

Figure 16 - Contingency Funds and Time Buffer Table	32

Figure 17 - Change Control Field List	33

Figure 18 - Master Plan	34

Figure 19 – Resources and Estimated Costs Per Work Package	36

Figure 20 – Loading Schedule	36

Figure 21 – Time Phased Budget	38

Figure 22 – Project Network Diagram	40

Figure 23 – Cost/Schedule Crashing	40

Figure 24 – Sample Status Report	40

Figure 25 – Status Report Data and Performance Metrics	40

# Introduction & Background

California lawmakers recently passed a resolution to increase the state’s share of renewable energy consumption to 33% by 2032. One source of this renewable energy lies in the Tehachapi Pass, Kern County. The biggest issue with this location is the energy must be transported and distributed via high voltage transmission lines to its intended destinations within southern California. See Figure 1 for a map of the full Tehachapi Project

This report covers the development and installation of a troublesome stretch of the transmission line stretching east towards SoCal’s inland empire – designation: Segment 8 Chino Hills. Following the approval of the project charter (Figure 2), the project management team at SoCal Edison (SCE) has been tasked with installing this section of transmission lines.

# Project Management Framework

## 2.1 Project Management Methodology

Due to this project’s nature of having a well-defined end goal and milestones, SCE used the Waterfall project management methodology to execute the project. Unlike the Agile methodology, which focuses on iterative processes and breaking up the phases of the project lifecycle, SCE benefits most from completing each project lifecycle phase in full before moving on to the next.

2.2 Project Selection Criteria/Model

To establish the project’s priority within SCE’s portfolio, we applied a Weighted Scoring Model (Figure 3) to all potential SCE projects. This model combines both qualitative and quantitative factors to ensure that SCE projects deliver financial returns, regulatory compliance, strategic alignment, and stakeholder value.

When applied, the Chino Hills 500kV Transmission Line achieved the highest composite score of 184, outperforming other candidates by at least 30+ points. This confirms that, despite its higher cost and complexity, the Chino Hills project is the optimal choice for SCE due to its regulatory necessity, renewable energy contribution, and strategic visibility.

# Organizational Alignment

3.1 Organizational & PM Structure

The Chino Hills 500kV Transmission Line is being executed under a Balanced Matrix structure. This structure ensures that the project benefits from both centralized leadership and specialized expertise. In this Structure, a dedicated Project Manager is responsible for overall coordination, schedule adherence and stakeholder engagement, while Functional managers (Engineering, Civil Construction, Procurement, Regulatory, and Community Relations) retain technical authority within their respective domains.

The Balanced Matrix structure allows SCE to leverage its diverse organizational expertise while maintaining the control necessary to deliver the project within the mandated regulatory and schedule constraints.

## 3.2 Resolving Resource Conflicts

One of the main challenges SCE’s multi-project focus and balanced matrix structure poses is conflicting resource demands. However, due to their similarities, separate segments of the Tehachapi project often require the same teams and resources, such as linemen, purchasing staff, heavy construction equipment, etc.

SCE’s strategy for mitigating these resource conflicts centers around a staggered approach, starting and finishing sections of the program at different times, limiting the number of active projects competing for resources, and allowing lessons learned from earlier sections to be utilized on later, more-challenging sections.

This approach also ensures that delays or overruns on any one project have a lower likelihood of endangering the overall project timeframe or budget, as early delays have time to be worked out, resources continue to be utilized during downtime on alternate projects, and projects with later starts are likely to experience fewer delays as more lessons are applied.

## 3.3 Stakeholder Analysis

Stakeholder Analysis (Figure 4) has been used to identify and assess the importance, influence, and interest of all individuals or groups who may be impacted by the project or can impact its outcome. Many of the non-SCE stakeholders played key roles in determining whether the project would proceed smoothly or face costly delays. The success of this project depended on the effective management of these stakeholders.

During the analysis we found that the CPUC, City of Chino Hills, and SCE executives were key players, requiring close engagement, continuous reporting, and active coordination to ensure approvals, funding, oversight, and regulatory compliance. California ISO and environmental regulators hold significant authority but lower day-to-day interest, so they were informed through milestone updates and timely compliance documentation. Residents and community groups, while not holding formal power, had high interest and as such were kept informed through transparent, but controlled communication to minimize opposition. Finally, contractors and vendors fall under minimal effort, requiring only standard updates and performance monitoring. This approach ensures stakeholder expectations are balanced and aligned to support smooth project execution.

3.4 Cultural Alignment

Cultural alignment played a decisive role in shaping the Chino Hills segment of the Tehachapi Renewable Transmission Project. SCE’s organizational culture emphasized technical feasibility, regulatory compliance, and cost efficiency. From this perspective, constructing overhead 500-kV transmission lines was the most rational and economical solution, given its proven technology, lower cost, and shorter construction timeline.

In contrast, the City of Chino Hills and its residents placed greater value on aesthetics, safety, environmental protection, and the preservation of property values. This bottom-up, community-driven perspective stood in opposition to SCE’s top-down, utility-first approach. As a result, strong cultural misalignment created a rift between SCE and the community.

Ultimately, regulatory feasibility, technological simplicity, faster delivery, and significantly lower costs outweighed community concerns and the CPUC allowed overhead lines to be constructed. While this decision allowed the project to move forward efficiently, it also left unresolved tensions with the City of Chino Hills and its residents that manifested as ongoing political or legal challenges in later phases.

3.5 Project Priority Matrix (Time–Cost–Performance Trade-offs)

The project used a Priority Matrix (Figure 5) to determine how to best manage trade-offs between time, Performance, and cost. This ensured decisions remained consistent with regulatory mandates, stakeholder expectations, and organizational goals. The resulting priorities were as follows:

- Performance – Constrain

- Cost – Enhance

- Time – Accept

# Planning & Controls

4.1 Work Breakdown Structure (WBS) & Coding system

The Work Breakdown Structure (WBS, Figure 7) for this project was created by systematically breaking down the overall scope (Figure 5) into progressively smaller, more manageable components. Its hierarchical structure ensured that no part of the project scope was overlooked and provided a clear roadmap for planning, scheduling, and assigning responsibility.

The WBS coding system follows a logical decimal structure that clearly identifies each level of detail. I.E. 5.1.2 refers specifically to Clearing & grading under Site Preparation (5.1), which falls under Site Easement (5).

This standardized system for tracking costs, resources, and schedule performance at multiple levels of detail allowed project managers to efficiently manage progress, monitor dependencies, and ensure alignment between deliverables and overall project objectives.

4.2 Responsibility Assignment Matrix (RAM) & WBS/OBS Integration

The Responsibility Assignment Matrix (RAM, Figure 8) is a tool that integrates the Work Breakdown Structure (WBS) with the Organizational Breakdown Structure (OBS) to clearly define who is responsible for each work package.

This integration allowed SCE’s project managers to align the project scope with organizational resources, making it easier to allocate work, monitor progress, and resolve responsibility overlaps or gaps. Ultimately, the RAM provided a structured framework that ensured all 25 work packages were assigned and managed effectively throughout the project lifecycle.

4.3 Communication Plan

The communication plan (Figure 10) shows the categories of information SCE is required to disseminate during the course of this project.

Much of the communication occurred internally at SCE. These internal communications were more frequent, ensuring the core project team’s ability to stay abreast of developments within the project.

External communication to vendors was also mandated on a regular basis to ensure project materials were produced and delivered in a timely manner. The goal of these communications was to prevent delays and give SCE the flexibility to change courses with ample time should a problem arise.

Conversely, public and regulatory disclosures and comment periods were held infrequently or as required by law. While the public’s needs are important to SCE, the company will not unnecessarily run the risk of its projects being bogged down or endangered by excessive public comment. These communications needed to be carefully crafted to prevent present tensions from growing.

# Estimating & Scheduling

5.1 Cost Estimation (Macro & Micro)

Bottom-Up Cost Estimates (Figure 11) showed overhead construction would leave SCE far below the $50 million budget. While this didn’t show financial pressure, the budget still revealed other interesting insights. The construction phases were projected to be the most expensive. Over two thirds of the project cost went towards the materials, site preparation, and construction phases of the project. As such, it was important that these phases were well-supported by the preceding activities.

5.2 Time Estimation

Time estimation in project management is the process of predicting the duration required to complete individual tasks, work packages, and the overall project. It helped establish realistic schedules, identify the critical path, allocate resources effectively, and assess whether the project can be delivered within mandated deadlines. Time estimates are crucial because they directly influence cost, scope, and resource planning, and they form the foundation of the project schedule and risk management processes.
For the Chino Hills 500kV Transmission Line, we applied a bottom-up approach, starting by assigning each work package a duration in days using expert judgment and reference to similar past projects. The resulting estimate of 1,195 days (around 3.3 years) provides the baseline timeframe for the project (not factoring concurrency) and will guide critical path analysis and deadline management against CPUC’s requirements.

To get a more accurate project duration we must look at the network diagram in the next section.

## 5.3 Network Diagram Development

In developing the Network Diagram (Figure 12) of 25 work packages, the activities and their dependencies were arranged into a logical sequence. This analysis showed that the project has two critical paths, with one of the sequences being:

1.1–>1.2–2.1–>3.1.1–>3.3.2–>4.1–>4.2–>5.1.2–>6.1.1–>6.1.2–>7.1.1–>7.1.2–>7.1.2–>7.2.1–>7.2.2.

The results showed that the activities on the two critical paths had the least amount of total slack (1,509 days), meaning they directly control the project’s completion time. Importantly, while many activities across the network exhibited high total slack, very few had substantial free slack. This condition made the project sensitive, meaning a small delay on one of the near-critical paths could easily consume the limited buffer and push that path into criticality.

# Risk & Change Management

6.1 Risk Management Process

In large-scale infrastructure projects such as the Chino Hills section of the Tehachapi Transmission Line project where regulatory, technical, and community issues intersect, structured risk management (such as was created in Figure 13 and Figure 14) is essential to project success.

The process typically involves the steps: Identification, Assessment, Ownership, Response Planning, and Monitoring.

## 6.2 Risk Responses & Mitigation Plans

A risk response plan defines how the project will deal with risks—whether by avoiding them, mitigating their impact, transferring responsibility, accepting them, or escalating them to higher authorities. A mitigation plan focuses on the concrete actions taken to reduce the likelihood or impact of a risk.

For the Chino Hills 500kV Transmission Line, risk responses and mitigation plans were applied across several high-priority areas as shown in Figure 15.

6.3 Contingency Funds & Time Buffers

Despite their comparatively low cost, the early stages of this project hold an outsized influence over the project’s success. Thus, more time needed to be held in contingency for these sections to ensure we had the flexibility needed to ensure success in the planning stages.

Similarly, greater contingency funds are allocated toward the construction phases of the project to buffer any cost overruns that may occur due to the likelihood that problems found in these sections would cost more money than the rest.

Figure 16 Shows the approximate amounts of time and money that were allocated to mitigate each risk.

6.4 Change Control Process

The change control process was controlled through a change control database application which kept track of the fields listed in Figure 17. The database had an interface available to as many SCE employees, managers, vendor representatives, and stakeholder representatives to enter change requests as possible. Approvals were routed through the chain of commands and stakeholders.

# The Master Plan

The Master Plan for the Chino Hills 500 kV Line Project (Figure 18) is a comprehensive roadmap that coordinates the project’s scope, schedule, cost, and quality objectives within a unified management structure. It ensured that every activity aligns with SCE’s strategic goals, regulatory obligations, California’s renewable energy mandates, and all stakeholders were cognizant of and aligned with these goals.

# Loading Schedule Development

The Loading Schedule (Figure 20) for the project was developed directly from the project’s network diagram presented in phase 1 and data pertaining to resources required per work package. The result is a time-based representation of when specific resources were engaged, serving as the operational link between the project network and the upcoming time-phased budget.

# Time-Phased Budget Development

The time-phased budget (Figure 21) for the project was developed by translating individual work package cost estimates into a schedule-based spending plan. This integration of schedule and cost creates a financial baseline directly linked to the critical path timeline to enable ongoing control and tracking of planned vs actual expenditures, early identification of cost variances, and realistic cash-flow projections aligned with SCE’s fiscal management practices.

# Resource Constraint

The resource data revealed that many critical activities rely on the same limited pool of specialized personnel, creating potential resource constraints that could affect schedule performance if not managed carefully. To address these challenges, the project team applied resource leveling and resource constrained scheduling to get a more accurate view of how long the project would take. This proactive approach helped maintain the integrity of the updated project network and kept the Chino Hills 500 kV Line Project aligned with its baseline schedule and cost objectives.

# PM's Traits and Competencies, Team Development

In the Chino Hills 500kV Transmission Line Project, both Project Manager (PM) leadership and the overall Project Management framework were fundamental to achieving the project’s objectives within the constraints of cost, time, and scope. This project operated under a Balanced Matrix Organizational Structure that required close coordination among multiple functional departments including Engineering, Procurement, Construction, Environmental Compliance, and Community Relations.

The Project Manager acted as the central figure in integrating these departments, translating strategic objectives into executable plans, and ensuring that all activities remained aligned with the project’s purpose: the design, permitting, and commissioning of a 500kV transmission line that supports California’s renewable energy goals. At the same time, Project Management as a discipline provided the structured systems, procedures, and control mechanisms necessary to maintain alignment, manage risks, and ensure regulatory compliance throughout the project lifecycle.

The success of this project depended on how effectively Project Manager leadership and Project Management practices function together.

# Project Manager’s Traits and Competencies

The role of the Project Manager in the Chino Hills project was multifaceted and demanding, requiring not only technical understanding but also strong interpersonal and strategic leadership capabilities. The PM must coordinate technical teams, manage multiple stakeholders, and make critical decisions while maintaining accountability for safety, environmental, and regulatory outcomes.

The following key traits and competencies defined effective Project Management leadership in this project:

- Leadership and Strategic Vision

- Technical and Analytical Expertise

- Strategic Decision-Making and Problem-Solving

- Stakeholder and Communication Management

- Ethical Responsibility and Accountability

- Change and Risk Management Expertise

Through these combined traits and competencies, the Project Manager ensured that leadership and execution remained synchronized. This balance between human capability and structured management allowed the project to maintain momentum and achieve both technical and organizational goals.

# Project Management and Team Development

While the Project Manager provided strategic direction, the broader Project Management framework established the organizational foundation for teamwork, communication, and control. The project team consisted of professionals from multiple departments, each contributing expertise in their respective domains. The effectiveness of Project Management lies in developing this diverse group into a cohesive, high-performing team capable of executing complex technical and logistical tasks.

The Chino Hills 500kV Transmission Line Project applied a structured and deliberate approach to team development based on Bruce Tuckman’s model of Forming, Storming, Norming, Performing, and Adjourning.

# Technology Challenge and Schedule Opportunity

## 14.1 Challenges we faced — and how we handled them

1. While building, the biggest call was choosing whether to route the transmission lines overhead vs. underground. Underground would ease visuals and smooth relations with the residents of Chino Hills, but at 500 kV it would require first-of-their-kind duct banks, joint bays, thermal backfill, long splicing/testing, and extra permits— all taking more time and at greater cost risk.

The decision was made to push forward with overhead lines with the knowledge that this would have repercussions that needed to be mitigated. To ensure the installation would go smoothly, the project management team scheduled biological, geological, and regulatory surveys before installation, used dust/noise controls, kept environmental monitors on site, and set clear work windows. The project management team also kept a steady cadence with CPUC and the City of Chino Hills, requiring any requirements changes stemming from this challenge went through change control, so schedule and costs stayed predictable.

2. Another issue was that the electrical and wiring diagrams did not fully align with actual substation conditions. This created a hazard for both the installation process and future maintenance operations. As failure of the electrical diagrams could jeopardize acceptance of delivery of the transmission lines, the project management team quickly began performing a strategic recovery to keep the project on track.

The test technician was instructed to redline (mark changes to the original in red pencil) the substation drawings with the necessary revisions. The original design teams were then called back from their new projects to ensure accurate documentation was created from these redlined drawings. Once the drawings were up to date and ready for use, the final delivery could take place with only a minor delay.

14.2 Opportunity we used — targeted crashing

Once the network diagram was created and set, an opportunity was identified to crash multiple critical activities. Only tasks that were on the critical path were accelerated, and the schedule was reevaluated after each move. Through crashing five work packages—Project Charter, Scope of Work, Route Alignment, Cable drum delivery & setup, and As-built documentation—the total duration was cut from 2,191 days to 2,142 days (49 days saved). Direct costs rose about $51,000 but indirect costs fell by $58,800, resulting in a decrease in a net change in costs of $7,800.

Overall, handling the overhead/underground challenge swiftly, strategically recovering from the discovery of inaccurate drawings late in the project, and utilizing targeted crashing meant the project finished earlier, cost slightly less in total, and confidence in the project was strengthened with regulators, the city, and residents.

# Status Reports

Status reports for the project were a way for project managers and stakeholders to keep abreast of progress and developments in the project. For this particular project, status reports were created and sent out on the first day of every month. A sample status report has been included in Figure 24.

# Performance Metrics and Indexes

The data for this section can be found in Figure 25.

Project managers quantified the status of the project at the end of each project period in terms of schedule and budget over/underruns, as well as projected the data into the future to estimate final project totals for those same categories using the Earned Value Data section of the status report. This section of the status reports utilized Earned Value (EV) data, Planned Value (PV) data gathered from the Time Phased Budget, and Actual Costs (AC) gathered from accounting software.

In order to quantify the project as over or under the budget or schedule at the time each status report captures, two metrics were utilized: the Cost Performance Index (CPI) - a measure of how much work has been done per dollar spent, and the Scheduling Performance Index (SPI) - a measure of how much work has been done per dollar expected to be spent by that point.

This data can be expanded further by projecting current cost totals into the future to see whether the project is on track to finish with favorable spending compared to the budget. Estimated Cost to Complete Work (ETC) works by finding the remaining EV left to gain and dividing it by the CPI. The Actual Cost at Completion (EAC) is an extension of this that adds the AC to the ETC. Finally, the expected cost is subtracted from the EAC to get the expected Cost Variance at Completion (VAC).

# Project Closure

Due to the multi-project landscape of SCE and the highly regulated nature of the industry in which it operates, project closure for the Chino Hills section of the Tehachapi Project was a daunting task. Each and every project SCE completes must follow strict regulations in order to comply with laws and ordinances, all of which affect final delivery needs and activities.

Nevertheless, the project manager oversaw the smooth transition of employees and a successful handoff of project deliverables to the customer (in this case, another division of SCE) at the end of the Chino Hills Transmission line project.

## 17.1 Project closure Activities

For the Chino Hills portion of the Tehachapi Renewable Transmission project, major project closure activities included the following:

- Final tests and certification (analogous to delivery acceptance)

- Energizing (analogous to delivery)

- Performing a post project audit and team evaluation

- Shutting down and releasing project resources and team members

- Closing accounts

- Creating the final report

## 17.2 Delivery Acceptance and Delivery

The work breakdown sheet from Phase 1 shows that the end of the project consisted of work packages for final testing, certification, and energization tasks. Together, these packages accounted for the project closure tasks of delivery acceptance and delivery.

## 17.3 Performing a Post-Project Audit and Team Evaluation

As the project began to wind down, the Project Management team began to schedule performance reviews with each team member of the project. Concurrently, the project management team began a post-project audit. The post-project audit and performance reviews were utilized to inform future decisions about team placement and will continue to provide valuable feedback on how to better manage future projects within SCE.

## 17.4 Shutting down the project

Many different teams and resources were pulled for the Chino Hills section of the Tehachapi Renewable Energy Transmission Project, many of which were utilized and shared multiple sections of the overarching program. At the closure of the Chino Hills section, the main challenge was ensuring that the teams and resources remaining on the project were reassigned and utilized quickly for these and other projects in the SCE project portfolio. With good planning and forethought, most teams were fully transitioned to their new assignments within days of project closure.

## 17.5 Closing Accounts

Once the project came to a close, it was time to close accounts for the project. Using expense tracking software, all actual costs associated with the project had been tracked. Using this information, all vendors and employees were paid, and backup documentation was kept orderly for future audits. Only a few minor payment discrepancies with vendors were discovered and handled regarding late payment charges that had not been entered into SCE’s books.

## 17.6 Final Report

Once the project was delivered, the project management team needed to complete a post-project audit.

Similar metrics to the status reports would be analyzed in the final report to find out whether final goals of cost and time were met. As SCE completes variations of this transmission line project regularly (though most are on a smaller scale), the results are expected to be used to inform SCE in similar future projects.

The final report was made available to SCE’s project management teams through the SCE project portfolio and tracking database.

# Where is SCE on the Project Management Maturity Model

This project reflects Level 4 of the Project Management Maturity Model, as SCE maintains a mature Management of Project Office (MPO) department and practices portfolio project management to ensure strategic alignment across initiatives. Finally, performance appraisals were conducted by departmental managers to evaluate team effectiveness, recognize contributions, and identify areas for development. These steps demonstrate SCE’s commitment to structured project governance, organizational learning, and long-term operational excellence.

# Conclusion and Lessons Learned

The Chino Hills 500kV section of the Tehachapi Reliability Transmission Project (TRTP) representsed an immense effort to modernize regional electric power capacity and operational efficiency through careful planning, coordination and execution. Throughout the project, the integration of technical analysis, risk assessment, and optimizing the schedule ensured that design and construction of deliverables aligned with SCE’s safety standards and regulatory requirements. The project demonstrated how early stakeholder engagement, consistent communication, and a balanced matrix organizational structure contributed to timely decision-making and reduced uncertainty during implementation.

In reflection, a complex project of this magnitude also demonstrated the critical role of collaboration, adaptability, and authentic leadership in achieving project success.  The lessons learned from this project will inform future transmission infrastructure projects, highlighting the value of transparent communication, rigorous planning, and team synergy in overcoming complexity.  This is another example of SCE leading through innovation, turning complex challenges into opportunities to modernize the grid, strengthen reliability, and set new standards for other utilities to follow on project delivery. The Chino Hills 500 kV section stands as a model of how commitment, foresight, and innovation can power a more resilient energy future.

# Figures

## Figure 1 - Map of overarching Tehachapi Project (link to source)

## Figure 2 – Project Charter

Business Case:

As part of the Tehachapi Renewable Transmission Project, a section of the transmission lines is required to pass through the city of Chino Hills. This project has two possible routes using existing utilities easements, the option to put the transmission lines above or below ground, and a deadline imposed by the California Public Utilities Commission (CPUC) of 6 years after project initiation due to the state’s 33% renewable energy mandate within 10 years of project initiation. Our company, Southern California Edison (SCE), has been tasked with planning and executing this part of the project.

Brief Project Scope of Work:

For this project, SCE will be required to

- Choose a route for the transmission lines

- Choose whether to run the lines above or below ground

- Construct and install of the necessary components, both structural and functional

- Test, validate, and commission the transmission line

Risk and Spending Limits:

Expenditures are capped at CPUC-approved amounts. Any overruns require executive approval. Budget oversight will be maintained at all stages. Risk tolerance is low. Primary risks include: public opposition, schedule delays, cost escalation, and unforeseen complexity. Mitigation: contingency design reviews, contractor monitoring, and proactive community engagement.

Team Composition and Stakeholders:

The team will consist of a dedicated cross-functional group including members from SCE’s Engineering, Project Management, Construction, Environmental Services, and Community Relations departments. The team will also interface with contractors, vendors, and local agencies as needed. Stakeholders include SCE (Southern California Edison), the City of Chino Hills, California Independent System Operator (ISO), CPUC (California Public Utilities Commission), environmental regulators, and local residents.

## Figure 3 - Project Selection/Criteria Model

The criteria used for evaluation were:

- Regulatory Compliance: Alignment with CPUC mandates and federal/state permitting requirements.

- Renewable Energy Focus: Contribution to California’s 33% renewable energy integration goal.

- Core Competencies: Fit with SCE’s established expertise in engineering, construction, and transmission line management.

- Profitability/Cost Reduction Potential: Long-term operational savings, reduced reliance on non-renewable energy, and cost efficiency.

- Urgency: Time sensitivity driven by regulatory deadlines and system reliability requirements.

- Government Subsidies: Availability of external funding or incentives for renewable infrastructure.

- Strategic Alignment: Degree of alignment with SCE’s mission, California’s renewable energy policy, and community needs.

- Project Cost: Overall cost considerations, with higher-cost projects receiving lower scores unless justified by strategic or regulatory needs.

These criteria were applied using a weighted scoring model. Each factor was assigned a weight based on its importance (e.g., Strategic Alignment = 8, Urgency = 7, Profitability = 6), and candidate projects were scored accordingly.

## Figure 4 - Stakeholder Analysis Table

| Stakeholder | Power | Interest | Category | Engagement Strategy |
| --- | --- | --- | --- | --- |
| California Public Utilities Commission (CPUC) | High | High | Key Player | Engage closely; frequent reporting, ensure regulatory compliance, early approval checks. |
| City of Chino Hills | High | High | Key Player | Active engagement; regular coordination on ROW permits, community relations, local safety. |
| SCE Executives / Project Sponsor | High | High | Key Player | Continuous updates; involve in cost/schedule oversight, executive approvals for changes. |
| California ISO | High | Low | Keep Satisfied | Provide milestone updates; engage when grid reliability issues arise. |
| Environmental Regulators | High | low | Keep Satisfied | Ensure compliance documentation and timely permit approvals; periodic reporting. |
| Residents & Community Groups | High | High | Keep Satisfied | Town halls, newsletters, and transparent updates to minimize opposition and build trust. |
| Contractors & Vendors | Low | Low | Minimal Effort | Standard contractual updates, progress reports, and compliance checks. |

## Figure 5 - Project Scope of Work

Project Scope of Work

| Project Objective | Design and construct the Chino Hills segment of the Tehachapi Renewable Transmission Project’s 500kV transmission line. Supports California’s 33% renewable energy mandate by 2032, at a cost of less than $50 million. |
| --- | --- |
| Project Scope Description | Energized 500kV transmission lines through Chino Hills that will connect the LA county and San Bernardino County segments of the Tehachapi Renewable Transmission Line. Low impact on the environment. |
| Justification | California has mandated that SCE increase the share (%) of its energy that comes from renewable sources. The Tehachapi project is meant to increase that share significantly to keep the company within regulatory limits. The Chino Hills segment of the transmission line is the final link needed to bring this renewable energy to SCE’s customer base. |
| Deliverables | - Pre-project materials - regulatory approvals and permits - Route specification - Tower and grounding system design documents - Vendor qualifications - Construction materials - Constructed towers - Installed cable - Final tests - Documentation |
| Milestones | - Permits and approvals acquired - Designs finalized - Vendors approved and materials acquired - Sites Prepared - Towers Constructed - Cables installed - Final checks complete |
| Technical Requirements | - The finished transmission lines must be capable of transmitting 500kW continuously. - Seismic stability. Transmission will occur over an active fault line. - Power lines must be a minimum distance apart to prevent arcing, including in high wind scenarios. - Power lines must be a minimum distance from homes as set by the CPUC. |
| Limits and Exclusions | Risk tolerance is low. Primary risks: schedule delays, cost escalation, and community pushback/litigation. Mitigation: contingency design reviews, contractor monitoring, and proactive community engagement. Expenditures are capped at CPUC-approved amounts of $50 million. Any overruns require executive approval. Budget oversight will be maintained at all stages. |
| Acceptance Criteria | - Power lines are constructed, installed, and spliced with the next sections of the Tehachapi transmission project. - Energization tests passed - Documentation created |

## Figure 6 - Project Priority Matrix

| Criteria | Priority | Description |
| --- | --- | --- |
| Performance | Constrain | Must meet 500kV technical, regulatory, and safety requirements. |
| Cost | Enhance | Budget efficiency prioritized. While capped at $50M, flexibility is allowed with approvals from Executives. |
| Time | Accept | Flexible within 6-year CPUC deadline tied to California’s 33% renewable goal, supported by a multi-year buffer. |

## Figure 7 - Work Breakdown Structure

1. Project Management

- 1.1 Issue Project charter

- 1.2 Create Scope of Work

2. Regulatory & Environmental

- 2.1 Regulatory Permits

- 2.2 Environmental Compliance planning

3. Prototypes and Designs

- 3.1 Corridor Identification

- 3.1.1 Route alignment

- 3.1.2 Seismic design & load studies

- 3.2 Civil & Structural Design

- 3.2.1 Footing design

- 3.2.2 Tower structure design

- 3.3 Electrical & Protection Design

- 3.3.1 Cable sizing & specification

- 3.3.2 Grounding system design

- 3.3.3 Relay/protection coordination

4. Materials Procurement

- 4.1 500kV cable procurement

- 4.2 Tower Structural Materials

5. Site Easement

- 5.1 Site Preparation

- 5.1.1 Surveying & staking

- 5.1.2 Clearing & grading

- 5.2 Tower Construction

- 5.2.2 Tower structure construction

- 5.2.3 Tower structure Assembly

6. Cable Installation

- 6.1 Cable Pulling

- 6.1.1 Cable drum delivery & setup

- 6.1.2 Cable pulling operations

- 6.1.3 Cable Splicing

- 6.1.4 Cable Testing

7. Commissioning & Closeout

- 7.1 System Energization

- 7.1.1 Pre-energization checklist

- 7.1.2 Energization testing

- 7.2 Project Closeout

- 7.2.1 As-built documentation

- 7.2.2 Lessons learned Report

## Figure 8 - Responsibility Assignment Matrix

## Figure 9 - WBS/OBS Integration

## Figure 10 - Communication Plan

| What Information | Target Audience | When? | Method of Communication | Provider |
| --- | --- | --- | --- | --- |
| Project Proposals for public comment | CPUC, City of Chino Hills, Chino Hills Residents | Prior to choosing route | Town hall meeting | Project Manager, Public Relations |
| Proposal Decision | City of Chino Hills, Chino Hills Residents, SCE Senior Management | After CPUC has made decision on over heading and route has been chosen | Website Bulletin, Management Meeting | Project Manager, Public Relations |
| Milestone Report | SCE Senior Management, Project Manager | Bimonthly | E-mail | Department Heads |
| Project Status Reports and Agendas | CPUC, SCE, applicable vendors | Weekly | E-mail | Project Manager |
| Department Status Reports | Project Manager | Weekly | E-mail | Department Heads |
| Issues Report | CPUC, SCE Senior Management | Weekly | E-mail | Project Manager |
| Vendor Status Reports | Project Manager, Department Heads | Bi-monthly | E-mail | Vendors |
| Accepted Change Requests | SCE Management, CPUC, Department Heads, applicable vendors | As needed | E-mail | Project Manager |
| Oversight Decisions | Project Staff, SCE, Project Manager | As needed | CPUC minutes/rulings website pages | CPUC |

## Figure 11 - Cost Estimation (Macro and Micro)

| Work Packages | Cost (Micro) ($) | Cost (Mid) ($) | Cost (Macro) ($) |
| --- | --- | --- | --- |
| 1. Project Management | - | - | $20,000.00 |
| 1.1 Project charter | $10,000.00 | $20,000.00 | - |
| 1.2 Scope of Work | $10,000.00 | - | - |
| 2. Regulatory & Environmental | - | - | $125,000.00 |
| 2.1 Regulatory Permits | $50,000.00 |  | - |
| 2.2 Environmental Compliance | $75,000.00 |  | - |
| 3. Prototypes and Designs | - | - | $870,000.00 |
| 3.1 Corridor Identification | - | $60,000.00 | - |
| 3.1.1 Route alignment | $30,000.00 | - | - |
| 3.1.2 Seismic design & load studies | $30,000.00 | - | - |
| 3.2 Civil & Structural Design | - | $500,000.00 | - |
| 3.2.1 Footing design | $200,000.00 | - | - |
| 3.2.2 Tower structure design | $300,000.00 | - | - |
| 3.3 Electrical & Protection Design | - | $310,000.00 | - |
| 3.3.1 Cable sizing & specification | $40,000.00 | - | - |
| 3.3.2 Grounding system design | $150,000.00 | - | - |
| 3.3.3 Relay/protection coordination | $120,000.00 | - | - |
| 4. Materials Procurement | - | $5,500,000.00 | $5,500,000.00 |
| 4.1 500kV cable procurement | $3,000,000.00 | - | - |
| 4.2 Tower Structural Materials | $2,500,000.00 | - | - |
| 5. Site Easement | - | - | $5,050,000.00 |
| 5.1 Site Preparation | - | $1,350,000.00 | - |
| 5.1.1 Surveying & staking | $150,000.00 | - | - |
| 5.1.2 Clearing & grading | $1,200,000.00 | - | - |
| 5.2 Tower Construction | - | $3,700,000.00 | - |
| 5.2.2 Tower structure construction | $1,200,000.00 | - | - |
| 5.2.3 Tower structure Assembly | $2,500,000.00 | - | - |
| 6. Cable Installation | - | - | $3,300,000.00 |
| 6.1 Cable Pulling | - | $3,300,000.00 | - |
| 6.1.1 Cable drum delivery & setup | $100,000.00 | - | - |
| 6.1.2 Cable pulling operations | $2,500,000.00 | - | - |
| 6.1.3 Cable Splicing | $600,000.00 | - | - |
| 6.1.4 Cable Testing | $100,000.00 |  | - |
| 7. Commissioning & Closeout | - | - | $450,000.00 |
| 7.1 System Energization | - | $250,000.00 | - |
| 7.1.1 Pre-energization checklist | $150,000.00 | - | - |
| 7.1.2 Energization testing | $100,000.00 | - | - |
| 7.2 Project Closeout | - | $200,000.00 | - |
| 7.2.1 As-built documentation | $150,000.00 | - | - |
| 7.2.2 Lessons learned Report | $50,000.00 | - | - |
| Total |  |  | $15,315,000.00 |

## Figure 12 - Base Network Diagram

## Figure 13 - Risk Table

| Risk ID | Risk Description | Cause/Source | Owner |
| --- | --- | --- | --- |
| R1 | Public opposition or protests | Community concerns over safety, EMF exposure, noise | Project Manager/ Community Relations |
| R2 | Delay in CPUC approval | Delay in review, missing documentation | Regulatory Affairs |
| R3 | Environmental non-compliance | Dust, noise, wildlife disruption and potential hazardous material spillages. | Regulatory Affairs |
| R4 | Vendor supply chain delay | Vendor qualification delays, long lead times for 500kV cables & tower materials | Procurement Lead |
| R5 | Cable splicing or testing failure | Design Errors, Workmanship issue (Flaws in the engineering of the system, such as incorrectly sized equipment, insufficient structural capacity for towers, or incomplete drawings) | Engineering lead/Procurement lead |
| R6 | Construction complexity & unforeseen ground issues | Seismic faults, soil instability, access challenges | Construction Lead |
| R7 | Worker injury or accident | High-voltage handling, heavy equipment | Construction Lead |
| R8 | Budget overrun | Underestimated costs, scope creep | Project Manager |
| R9 | Ineffective stakeholder communication | Misalignment between CPUC, city, contractors | Project Manager |
| R10 | Extreme weather impacts | Heavy rain, heat waves | Construction Lead |
| R11 | Labor strikes or shortage | Union disputes, lack of skilled cable jointers | Procurement Lead |
| R12 | Seismic Activity | Earthquakes occur in the area frequently. Earthquakes of sufficient size to cause damage or risk to the project, however, are rare. | Accept |

## Figure 14 - Risk impact Matrix

| Probability / Impact | Low | Medium | High |
| --- | --- | --- | --- |
| Unlikely |  |  | R12 |
| Moderate |  | R3,R7,R8,R11 | R4,R5,R6 |
| Very Likely | R10 | R2 | R1,R9 |

## Figure 15 - Risk Response and Mitigation Table

| Analysis | Monitoring | Response Strategy | Strategy |
| --- | --- | --- | --- |
| High likelihood of community pushback; could cause major schedule delays. | Weekly - Track community complaints, monitor media & social platforms | Mitigate and Escalate | Escalate to Senior Management / Local Government -Resolve disputes where possible and maintain project continuity if community pressure escalates |
| CPUC delays are common; impacts project start date. | Bi-Weekly - Review permit approval status, direct CPUC updates | Mitigate | Submit complete docs early, follow up regularly, monitor CPUC status |
| Regulatory fines possible, but impact contained if monitored. | Weekly - Site inspections, environmental audit reports | Mitigate | Regular site inspections, environmental audits, dust/noise control, wildlife monitoring |
| Any delay in getting materials to the work site delays the project completion date | Weekly - Vendor delivery reports, milestone tracking | Mitigate / Transfer | Track vendor milestones, maintain multiple suppliers, order long-lead items early. Transfer to Vendors (via contractual obligations with penalties) |
| Unlikely, potential to be highly disruptive if not caught during testing | Per Test Cycle - Quality control tests, engineering signoffs | Mitigate & Accept | Quality control tests, design peer review, backup components ready. Be prepared for Minor failures absorbed within testing schedule |
| Soil instability and seismic risks significant in Chino Hills. | Daily Before starting the construction and weekly once the construction is started | Escalate | Senior Project Manager / Engineering Director - Geotechnical surveys, adjust construction methods, worker training |
| High safety risks involved with working with high voltage cables and heavy machinery; accidents could halt work temporarily. | Daily - Safety incident reports | Mitigate/ Transfer | Minor incidents can occur, Enforce PPE, safety drills, daily safety reporting, accident insurance |
| Contingency planning required; scope creep is a concern. | Monthly - Cost variance reports, earned value tracking | Escalate /Transfer | Senior Management - Track costs, control scope creep, review contracts. Transfer financial risk to contractors through fixed rate contracts and the government through budget increase clauses for mutually agreed changes in project requirements or expansions of scope. |
| Misalignment can cause rework and delays. | Bi-weekly - Meeting minutes, communication dashboard | Escalate | Escalate to Senior management to keep the project completion on track |
| Weather events are likely but can be planned for. | Seasonal - Weather alerts, contingency planning checks | Mitigate | Contingency plans for weather, flexible schedule, monitor alerts |
| Workforce availability risk due to union disputes. | Monthly - Based on union negotiations status | Transfer | Maintain buffer workforce, cross-train staff, negotiate labor agreements |
| Seismic events are unpredictable but rare. | Weekly - Check recent seismic activity for upticks in frequency and intensity as these could indicate increased likelihood for a major seismic event. | Accept | Keep all staff aware of safety protocols necessary for major seismic events, prepare emergency preparedness plans for each work site along the route |

## Figure 16 - Contingency Funds and Time Buffer Table

| Risk ID | Time Buffer | Contingency Funds |
| --- | --- | --- |
| R1 | 2 years | 10,000,000 |
| R2 | 9 months | $200,000 |
| R3 |  | $400,000 |
| R4 | 6 months |  |
| R5 | 3 months | $200,000 |
| R6 | 3 months | $400,000 |
| R7 |  | $2,000,000 |
| R8 |  | Management Funds |
| R9 | 3 month | $500,000 |
| R10 | 10 months | $1,,500,000 |
| R11 | 3 months | $2,000,000 |
| R12 |  | $1,000,000 |
|  | Management Funds for Project | $8,200,000 |

## Figure 17 - Change Control Field List

- Unique change request IDs

- Description of the Change Request

- Status of the Change Request

- Date the request was opened

- Date the request was last updated

- Date the request was closed/completed

- Date request must be decided on (if applicable)

- Approximate Cost of the change

- Approximate delay caused by the change

- Who requested the change

- Who is assigned to bring the request through to closure/completion

- Comments on the change

- Relevant documents to the requested change

- Priority of the change

- Proposed funding source

- Reason for the change

- Approvals

## Figure 18 - Master Plan

Master Plan

Scope

The Chino Hills section of the Tehachapi Renewable Transmission Project will extend 3.5 miles between East and West Substations. The project will include development, installation, and testing of both the substations and overhead transmission lines between them.

Stakeholders

Sponsored by SCE, the project involves multiple oversight entities and stakeholders including the CPUC, WECC, CAISO, and the City of Chino Hills. Engineering and design service contracts have been contracted to Black & Veatch.

Communication Strategies

The project should put strong emphasis on stakeholder communication, community engagement, and risk management. Public outreach will be a key strategy in mitigating opposition and permitting and legal clearance will be sought to prevent unplanned delays.

Schedule

The project is projected to take 44 months to complete the following procedural approvals, with a deadline of 6 years to complete the project. Construction activities will be limited during extreme summer heat and holidays.

Budget

The project is estimated to cost $16,419,000.00 including direct and indirect costs. The total budget for the project is capped at CPUC-approved amounts of $50 million.

Labor and Resources

Labor and equipment for the project are expected to be shared with other phases of the Tehachapi project, adding complexity and likelihood of delays. Care will be taken to capitalize on opportunities to utilize free resources where possible to minimize these risks.

Performance Tracking

The project will be tracked and managed by an upward flow of information requiring lower-level managers to report progress up the chain. This information will be utilized to track performance with regular status reports available to all stakeholders.

## Figure 19 – Resources and Estimated Costs Per Work Package

## Figure 20 – Loading Schedule

## Figure 21 – Time Phased Budget

## Figure 22 – Project Network Diagram

## Figure 23 – Cost/Schedule Crashing

| Total Indirect cost | $1,104,000.00 |
| --- | --- |
| Saving per Unit Reduced | $1,200.00 |
| Duration | 2191 |
| Total Direct Cost | $15,315,000.00 |
| Actual cost | $16,419,000.00 |
| New Actual cost | $16,411,200.00 |
| New Duration | 2142 |

| Activity | Crash Cost | Maximum Crash Time | Normal Time | Normal Cost | Indirect Cost |
| --- | --- | --- | --- | --- | --- |
| Project charter | $2,000.00 | 2 | 10 | $10,000.00 | $2,000.00 |
| Scope of Work | $2,000.00 | 4 | 20 | $10,000.00 | $2,000.00 |
| Regulatory Permits | $15,000.00 | 5 | 20 | $50,000.00 | $10,000.00 |
| Environmental Compliance | $22,500.00 | 5 | 21 | $75,000.00 | $10,000.00 |
| Route alignment | $10,000.00 | 10 | 42 | $30,000.00 | $10,000.00 |
| Seismic design & load studies | $10,000.00 | 10 | 42 | $30,000.00 | $10,000.00 |
| Footing design | $70,000.00 | 12 | 48 | $200,000.00 | $50,000.00 |
| Tower structure design | $100,000.00 | 12 | 48 | $300,000.00 | $75,000.00 |
| Cable sizing & specification | $12,000.00 | 7 | 28 | $40,000.00 | $10,000.00 |
| Grounding system design | $45,000.00 | 12 | 48 | $150,000.00 | $50,000.00 |
| Relay/protection coordination | $30,000.00 | 10 | 42 | $120,000.00 | $50,000.00 |
| 500kV cable procurement | $1,100,000.00 | 35 | 100 | $3,000,000.00 | $100,000.00 |
| Tower Structural Materials | $1,000,000.00 | 24 | 84 | $2,500,000.00 | $100,000.00 |
| Surveying & staking | $40,000.00 | 16 | 56 | $150,000.00 | $50,000.00 |
| Clearing & grading | $450,000.00 | 24 | 84 | $1,200,000.00 | $100,000.00 |
| Tower structure construction | $450,000.00 | 24 | 84 | $1,200,000.00 | $100,000.00 |
| Tower structure Assembly | $1,120,000.00 | 15 | 45 | $2,500,000.00 | $100,000.00 |
| Cable drum delivery & setup | $22,000.00 | 20 | 70 | $100,000.00 | $25,000.00 |
| Cable pulling operations | $1,120,000.00 | 40 | 105 | $2,500,000.00 | $100,000.00 |
| Cable Splicing | $240,000.00 | 20 | 70 | $600,000.00 | $75,000.00 |
| Cable Testing | $30,000.00 | 7 | 30 | $100,000.00 | $20,000.00 |
| Pre-energization checklist | $20,000.00 | 10 | 28 | $150,000.00 | $20,000.00 |
| Energization testing | $25,000.00 | 10 | 28 | $100,000.00 | $15,000.00 |
| As-built documentation | $15,000.00 | 13 | 28 | $150,000.00 | $10,000.00 |
| Lessons learned Report | $5,000.00 | 4 | 14 | $50,000.00 | $10,000.00 |

| Duration | 2191 | 2189 | 2185 | 2175 | 2155 | 2142 |
| --- | --- | --- | --- | --- | --- | --- |
| Activity |  | Project Charter | Scope of work | Route Alignment | Cable drum delivery & setup | As-built documentation |
| Actual Cost | $16,419,000.00 | $16,418,600.00 | $16,415,800.00 | $16,413,800.00 | $16,411,800.00 | $16,411,200.00 |
| Direct Cost | $15,315,000.00 | $15,317,000.00 | $15,319,000.00 | $15,329,000.00 | $15,351,000.00 | $15,366,000.00 |
| Indirect Cost | $1,104,000.00 | $1,101,600.00 | $1,096,800.00 | $1,084,800.00 | $1,060,800.00 | $1,045,200.00 |

## Figure 24 – Sample Status Report

Project Name: Tehachapi Project – Chino Hills Section

Date of Report: 2025-10-01

Brief Project Description – The Project covers the design, installation, and energizing of two substations and 500 kV transmission lines connecting them. These will be constructed in an existing energy corridor through the city of Chino Hills.

Earned Value Data

| Task | % Complete | EV | AC | PV | CV | SV |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 100 | 75 | 77 | 75 | -2 | 0 |
| 2.1 | 100 | 50 | 57 | 50 | -7 | 0 |
| 3.1.1 | 100 | 30 | 42 | 30 | -12 | 0 |
| 3.1.2 | 60 | 18 | 23 | 21 | -5 | -3 |
| 3.2.1 | 40 | 80 | 82 | 108 | -2 | -28 |
| 3.3.3 | 95 | 114 | 115 | 117 | -1 | -3 |
| 3.3.2 | 35 | 52.5 | 61 | 85 | -8.5 | -32.5 |
| Totals |  | 434.5 | 472 | 501 | -37.5 | -66.5 |

| Period |  | EV | AC | PV |  | SPI | CPI | PCI-B |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | 14 | 15 | 15 |  | 0.93 | 0.93 | 0.001 |
| 2 |  | 45 | 50 | 52 |  | 0.87 | 0.90 | 0.003 |
| 3 |  | 112 | 129 | 130 |  | 0.86 | 0.87 | 0.007 |
| 4 |  | 281 | 306 | 308 |  | 0.91 | 0.92 | 0.018 |
| 5 |  | 434.5 | 472 | 501 |  | 0.87 | 0.92 | 0.028 |
| EACf | = | 16636.78 |  | VACf | = | -1321.78 |  |  |

Status summary

The project is currently projected to be overbudget by about $1.3 million at completion. As it stands now, we are also somewhat behind schedule, but well within our generous time buffer. The project management team are prepared to utilize opportunities to decrease the schedule and costs where possible, however the main concern continues to be satisfactory completion of all required deliverables.

Explanations

This past period saw the project finish numerous critical activities of the project, allowing downstream activities to be pushed forward. Great time and cost savings were found in work package 3.1.1, however these were negated by expensive technical issues discovered and worked through in work package 3.2.1. The rest of the project continues at the scheduled pace.

Major changes since last report

- Design changes in the footing design work package 3.1.1.

Total cost of approved changes

~$20,000

Projected Cost at Completion

$16,636,780

Projected Completion Date

August, 2028

Current Risks

- Further discovery of as yet unknown technical requirements

## Figure 25 – Status Report Data and Performance Metrics

| Status Report: Ending Month 1 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 90 | 9 | 10 | 10 | -1 | -1 |
| 1.2 | 50 | 5 | 5 | 5 | 0 | 0 |
| Totals |  | 14 | 15 | 15 | -1 | -1 |
| Status Report: Ending Month 2 |  |  |  |  |  |  |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 40 | 30 | 35 | 37 | -5 | -7 |
| Totals |  | 45 | 50 | 52 | -5 | -7 |
| Status Report: Ending Month 3 |  |  |  |  |  |  |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 80 | 60 | 73 | 75 | -13 | -15 |
| 2.1 | 50 | 25 | 27 | 25 | -2 | 0 |
| 3.1.1 | 40 | 12 | 14 | 15 | -2 | -3 |
| Totals |  | 112 | 129 | 130 | -17 | -18 |
| Status Report: Ending Month 4 |  |  |  |  |  |  |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 100 | 75 | 77 | 75 | -2 | 0 |
| 2.1 | 90 | 45 | 53 | 50 | -8 | -5 |
| 3.1.1 | 60 | 18 | 29 | 30 | -11 | -12 |
| 3.1.2 | 50 | 15 | 15 | 15 | 0 | 0 |
| 3.2.1 | 25 | 50 | 53 | 53 | -3 | -3 |
| 3.3.3 | 40 | 48 | 50 | 51 | -2 | -3 |
| 3.3.2 | 10 | 15 | 14 | 19 | 1 | -4 |
| Totals |  | 281 | 306 | 308 | -25 | -27 |
| Status Report: Ending Month 5 |  |  |  |  |  |  |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 100 | 75 | 77 | 75 | -2 | 0 |
| 2.1 | 100 | 50 | 57 | 50 | -7 | 0 |
| 3.1.1 | 100 | 30 | 42 | 30 | -12 | 0 |
| 3.1.2 | 60 | 18 | 23 | 21 | -5 | -3 |
| 3.2.1 | 40 | 80 | 82 | 108 | -2 | -28 |
| 3.3.3 | 95 | 114 | 115 | 117 | -1 | -3 |
| 3.3.2 | 35 | 52.5 | 61 | 85 | -8.5 | -32.5 |
| Totals |  | 434.5 | 472 | 501 | -37.5 | -66.5 |

| Performance Indexes Summary |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Period |  | EV | AC | PV |  | SPI | CPI | PCI-B |
| 1 |  | 14 | 15 | 15 |  | 0.93 | 0.93 | 0.001 |
| 2 |  | 45 | 50 | 52 |  | 0.87 | 0.90 | 0.003 |
| 3 |  | 112 | 129 | 130 |  | 0.86 | 0.87 | 0.007 |
| 4 |  | 281 | 306 | 308 |  | 0.91 | 0.92 | 0.018 |
| 5 |  | 434.5 | 472 | 501 |  | 0.87 | 0.92 | 0.028 |
| EACf | = | 16636.78 |  | VACf | = | -1321.78 |  |  |