Tehachapi Reliability Transmission Project
 Chino Hill 500kV Section - Phase 2

Brian Montgomery
 Pearl Baghel
 Roberto Blanco

California State Polytechnic University, Pomona
 Course: EMT 6360 - Project Management

Fall 2025

Table of Contents

1. Introduction	2

2. The Master Plan	3

3. Loading Schedule Development	5

4. Time-Phased Budget Development	5

5. Resource Constraint	6

6. PM's Traits and Competencies, Team Development	7

7. Project Manager’s Traits and Competencies	7

7.1 Leadership and Strategic Vision	7

7.2 Technical and Analytical Expertise	8

7.3 Strategic Decision-Making and Problem-Solving	8

7.4 Stakeholder and Communication Management	8

7.5 Ethical Responsibility and Accountability	9

7.6 Change and Risk Management Expertise	9

8. Project Management and Team Development	9

Storming – Managing Early Conflicts and Integration	10

Norming – Building Cooperation, Trust, and Communication	10

Performing – Achieving High Efficiency and Synergy	10

Adjourning – Lessons Learned and Continuous Improvement	11

9. Technology Challenge and Schedule Opportunity	12

10. Status Reports	13

11. Performance Metrics and Indexes	14

12. Project Closure	15

12.1 Project closure Activities	15

12.2 Delivery Acceptance and Delivery	15

12.3 Performing a Post-Project Audit and Team Evaluation	16

12.4 Shutting down the project	16

12.5 Closing Accounts	17

12.6 Final Report	17

13. Where is SCE on the Project Management Maturity Model	17

14. Conclusion and Lessons Learned	18

By Project -	18

By EMT 6360 Project Group -	19

Appendix	19

Fig. 1 - Resources and Estimated Costs per Work Package	20

Fig. 2 - Loading Schedule	20

Fig.3 - Time Phased Budget	22

Fig. 4 - Project Network Diagram	24

Fig 6 – Sample Status Report	24

Fig. 7 – Status Report Data and Performance Metrics (Including Graph)	24

# 1. Introduction

The Tehachapi Renewable Transmission Project (TRTP) is a major initiative developed by Southern California Edison (SCE) to strengthen California’s electric grid and enable large-scale delivery of renewable energy to the Los Angeles Basin. The Chino Hills 500 kV Line Project, a 3.5-mile section of the 173-mile TRTP corridor, connects the East and West Substations within the City of Chino Hills. It forms part of Path 26, the vital transmission route linking northern and southern California power networks.

This compliance project played an essential role in helping the state achieve its Renewable Portfolio Standard (RPS), which requires that 33% of electricity come from renewable sources by 2030. Once operational, this section will transmit up to 4,500 megawatts of renewable power, supporting 4.5 million homes while integrating wind and solar energy from Tehachapi into Southern California’s electric grid.

Because of its location in a densely populated urban community, the project has drawn significant public attention and regulatory oversight. Stakeholders such as the California Public Utilities Commission (CPUC), Western Electricity Coordinating Council (WECC), California ISO (CAISO), and the City of Chino Hills have been deeply involved in shaping its completion. The design was outsourced to Black & Veatch, who provided engineering for tower structures, conductors, and geotechnical systems under strict compliance and SCE’s safety standards.

This report focuses on the tools available to project managers of this project to overcome challenges and seize opportunities presented during the project followed by a retrospective on the project itself.

# 2. The Master Plan

The Master Plan for the Chino Hills 500 kV Line Project is a comprehensive roadmap that coordinates the project’s scope, schedule, cost, and quality objectives within a unified management structure. It ensures that every activity aligns with Southern California Edison’s strategic goals, regulatory obligations, California’s renewable energy mandates, and all stakeholders are cognizant of and aligned with these goals. The following is the master plan in its entirety:

Master Plan

Scope

The Chino Hills section of the Tehachapi Renewable Transmission Project will extend 3.5 miles between East and West Substations. The project will include development, installation, and testing of both the substations and overhead transmission lines between them.

Stakeholders

Sponsored by SCE, the project involves multiple oversight entities and stakeholders including the CPUC, WECC, CAISO, and the City of Chino Hills. Engineering and design service contracts have been contracted to Black & Veatch.

Communication Strategies

The project should put strong emphasis on stakeholder communication, community engagement, and risk management. Public outreach will be a key strategy in mitigating opposition and permitting and legal clearance will be sought to prevent unplanned delays.

Schedule

The project is projected to take 44 months to complete the following procedural approvals, with a deadline of 6 years to complete the project. Construction activities will be limited during extreme summer heat and holidays.

Budget

The project is estimated to cost $16,419,000.00 including direct and indirect costs. The total budget for the project is capped at CPUC-approved amounts of $50 million.

Labor and Resources

Labor and equipment for the project are expected to be shared with other phases of the Tehachapi project, adding complexity and likelihood of delays. Care will be taken to capitalize on opportunities to utilize free resources where possible to minimize these risks.

Performance Tracking

The project will be tracked and managed by an upward flow of information requiring lower-level managers to report progress up the chain. This information will be utilized to track performance with regular status reports available to all stakeholders.

# 3. Loading Schedule Development

The Loading Schedule (See Fig.2) for the project was developed directly from the project’s network diagram presented in phase 1 and data pertaining to resources required per work package.

Each work package identified in the network was sequenced according to its logical dependencies, ensuring that start and finish times aligned with the overall project flow. Using the early and late start and finish dates (ES, LS, EF, LF) calculated in the network analysis, activities were positioned along the project timeline to define when work would occur. SCE resources information was then used to assign personnel such as Project Managers, Regulatory Specialists, and Geotechnical Engineers to each activity based on the packages’ estimated durations and required skill sets.

This integration of time and resource data produced the Loading Schedule, which clearly shows how labor and technical effort are distributed across the life of the project. The result is a time-based representation of when specific resources are engaged, serving as the operational link between the project network and the upcoming time-phased budget.

# 4. Time-Phased Budget Development

The time-phased budget (See Fig. 3) for the project was developed by translating individual work package cost estimates into a schedule-based spending plan. Each of the twenty five work packages had a defined duration, total cost, and resource assignment derived from the cost estimate stage. These costs were distributed across time according to the activity start and finish dates established in the project network. This integration of schedule and cost creates a financial baseline that identifies when expenditures are expected to occur, essential for forecasting cash flow and measuring earned value.

This process is showcased by the following example. The “500 kV Cable Procurement” work package (WP 4.1) carries a total budget of $3 million and a 100-day duration. The cost was spread evenly across the months of planned procurement activity, starting in the seventh month, reflecting a steady disbursement as materials are ordered, inspected, and delivered. Similar logic was applied to all work packages, using a 5-day workweek calendar consistent with construction and engineering practices. The nine standard annual SCE holiday are observed, however they have a negligible impact on project cost or timing.

This time-phased budget now serves as the cost performance baseline, directly linked to the critical path network used in prior scheduling analysis. It enables ongoing control of planned versus actual expenditures, early identification of cost variances, and realistic cash-flow projections aligned with SCE’s fiscal management practices.

# 5. Resource Constraint

As the project network evolved into a detailed loading schedule, several key activities were identified as critical to maintaining the overall timeline. The resource data reveals that many of these high-priority activities rely on the same limited pool of specialized personnel, creating potential resource constraints that could affect schedule performance if not managed carefully.

For instance, the Project Manager (PM) (See Fig.1) supports multiple early-phase tasks such as project initiation and scope development. Because these foundational activities drive the sequencing of later work, any delay in their completion due to overcommitment could shift the entire schedule forward. For example, per the project network, the Regulatory Specialist (RS) and Compliance Specialist (CS), assigned to permitting and environmental compliance, represent potential bottlenecks, as their work must be completed before several design and procurement packages can begin. Their limited availability during early phases makes them critical from both a resource and schedule standpoint.

Similarly, in the design and procurement stages, resource concentration increases further. The Structural Engineer (SE) and Electrical Engineer (EE) are assigned to multiple concurrent design tasks, such as tower structure and grounding system design, as well as material procurement. Without leveling the schedule, these overlapping assignments could exceed individual capacity, creating delays in deliverables that have little or no slack in the schedule. The same logic applies to the Logistics Coordinator (LC) who plays a central role during procurement and material handling; if this resource becomes overallocated, it could hinder material readiness for field construction activities.

To address these challenges, the project team should apply resource leveling and resource constrained scheduling, such as shifting noncritical activities, redistributing workloads, or supplementing additional support staff during peak demand. Regular review of resource loading across project phases will ensure that no critical activity is delayed due to personnel constraints. This proactive approach helps maintain the integrity of the updated project network and keeps the Chino Hills 500 kV Line Project aligned with its baseline schedule and cost objectives.

# 6. PM's Traits and Competencies, Team Development

In the Chino Hills 500kV Transmission Line Project, both Project Manager (PM) leadership and the overall Project Management framework are fundamental to achieving the project’s objectives within the constraints of cost, time, and scope. This project, part of SCE broader renewable energy expansion initiative, operates under a Balanced Matrix Organizational Structure that requires close coordination among multiple functional departments including Engineering, Procurement, Construction, Environmental Compliance, and Community Relations.

The Project Manager acts as the central figure in integrating these departments, translating strategic objectives into executable plans, and ensuring that all activities remain aligned with the project’s purpose the design, permitting, and commissioning of a 500kV transmission line that supports California’s renewable energy goals. At the same time, Project Management as a discipline provides the structured systems, procedures, and control mechanisms necessary to maintain alignment, manage risks, and ensure regulatory compliance throughout the project lifecycle.

The success of this project depends on how effectively Project Manager leadership and Project Management practices function together. The PM provides the human and strategic elements of vision, leadership, and communication while Project Management provides the procedural foundation planning, scheduling, budgeting, risk management, and performance monitoring. Both are interdependent and equally essential.

# 7. Project Manager’s Traits and Competencies

The role of the Project Manager in the Chino Hills project is multifaceted and demanding, requiring not only technical understanding but also strong interpersonal and strategic leadership capabilities. The PM must coordinate technical teams, manage multiple stakeholders, and make critical decisions while maintaining accountability for safety, environmental, and regulatory outcomes.

The following key traits and competencies define effective Project Management leadership in this project:

## 7.1 Leadership and Strategic Vision

The Project Manager provides the guiding vision that aligns all team members with the project’s overarching objectives. This leadership anchors the project with a clear strategic intent from delivering the approved Chino Hills 500 kV alignment within the CPUC constraints while safeguarding cost, schedule, and community commitments.

To make that happen, the Project Manager keeps track of the project scope, builds a simple task plan so every team knows its job and handoffs, and sets decision rules so that there is no delay in making decisions. When choosing between overhead and underground transmission lines, the Project Manager played an important role in leading the team towards the determination that overhead was the best route due to simpler construction, lower cost, and a higher degree of schedule certainty.

Each week the Project Manager reviews the basic schedule, cost, and checks a short list of risks expected for the current phase of the project. If the schedule slips, it is the PM who re-schedules work packages to protect the finish date, shifts crews to where they can be most effective, speeds up key purchases, and uses management reserves to acquire more resources to fill the gaps. This steady leadership and clear vision keep the plan under control and capture lessons learned at each phase, so the project can run smoothly.

7.2 Technical and Analytical Expertise	
Given the project’s engineering complexity, the PM must possess a deep understanding of transmission line design, seismic load analysis, and high-voltage system integration. This expertise allows for informed decision-making when evaluating design alternatives, optimizing construction methods, and mitigating technical risks. The PM’s technical knowledge bridges communication between engineers, contractors, and SCE management, ensuring that technical challenges are resolved effectively while maintaining control over the $16.5 million project budget and 6-year schedule.

7.3 Strategic Decision-Making and Problem-Solving
Effective Project Management requires the ability to assess situations quickly, anticipate potential risks, and implement solutions that minimize impact. The PM applies decision-making tools such as the Critical Path Method (CPM), earned value analysis, and risk response matrices to evaluate trade-offs between time, cost, and scope. Through analytical reasoning, the PM identifies alternative strategies when delays or cost escalations arise, executing a strategic recovery plan, and ensuring the project remains adaptable and resilient under evolving conditions.

7.4 Stakeholder and Communication Management
One of the PM’s most critical competencies is communication. The Chino Hills project involves a diverse set of stakeholders including SCE executives, state and city regulatory bodies, environmental agencies, contractors, vendors, and the local community. The PM ensures continuous and transparent communication across all these channels through structured updates, stakeholder meetings, progress reports, and information-sharing systems. This not only builds trust but also minimizes misunderstandings and miscommunications that can lead to opposition or project delays.

7.5 Ethical Responsibility and Accountability
The PM ensures that all project actions and decisions adhere to the highest standards of professional ethics, environmental stewardship, and safety compliance. Given the project’s environmental sensitivity and community visibility, the PM emphasizes sustainable practices, fair labor engagement, and transparent procurement. Ethical accountability reinforces SCE’s reputation as a responsible organization and ensures long-term community support.

7.6 Change and Risk Management Expertise
The PM is responsible for maintaining control over all project changes and risks through structured Project Management processes. An example of this is a change control system that can be implemented to log, track, and evaluate any requirement modifications that may affect cost, schedule, or scope. Each change request undergoes a formal approval process, ensuring that decisions are data-driven and properly documented. Likewise, continuous risk management including risk identification, assessment, and mitigation planning ensures that potential threats are proactively managed, protecting project performance.

Through these combined traits and competencies, the Project Manager ensures that leadership and execution remain synchronized. This balance between human capability and structured management allows the project to maintain momentum and achieve both technical and organizational goals.

# 8. Project Management and Team Development

While the Project Manager provides strategic direction, the broader Project Management framework establishes the organizational foundation for teamwork, communication, and control. The project team consists of professionals from multiple departments, each contributing expertise in their respective domains. The effectiveness of Project Management lies in developing this diverse group into a cohesive, high-performing team capable of executing complex technical and logistical tasks. The Chino Hills 500kV Transmission Line Project applies a structured and deliberate approach to team development based on Bruce Tuckman’s model Forming, Storming, Norming, Performing, and Adjourning.

Forming – Establishing Structure and Foundation

At the project’s initiation, the PM and Project Management Office (PMO) focused on building a clear organizational foundation. Using the Work Breakdown Structure (WBS), the PM defined work packages for each major phase including design, permitting, procurement, construction, and testing. This step ensured that each department understood its exact responsibilities, deliverables, and reporting hierarchy. The Forming stage established order, clarity, and purpose setting the tone for disciplined collaboration across departments.

During this stage, the project team also introduced project charters, communication protocols, and coordination mechanisms (regular meetings, shared document repositories, and progress dashboards).

### Storming – Managing Early Conflicts and Integration

As departmental coordination intensified, natural conflicts began to emerge. The engineering team aimed to optimize cable routing and tower design for performance and cost, while the environmental team focused on minimizing ecological and noise impacts to satisfy CPUC and city permit conditions. These differences created tension in priorities and workflow. To manage this, we implemented structured integration meetings where conflicting requirements were openly discussed. The PM acted as a facilitator, promoting transparent communication and ensuring that all voices were heard. Through negotiation and shared understanding, this phase transformed potential friction into cooperative problem-solving. The outcome was a more aligned team and better mutual respect among disciplines.

### Norming – Building Cooperation, Trust, and Communication

Once early challenges were resolved, the project entered a period of stabilization. The PM emphasized developing consistent communication habits, cross-functional collaboration, and trust among team members. Weekly coordination meetings were formalized, and joint review sessions were held to synchronize engineering progress with regulatory milestones and procurement status. A project dashboard was created to track progress in real-time, integrating cost, schedule, and risk metrics accessible to all departments.

To strengthen team identity, we recognized key milestones (such as regulatory submissions and design approvals) and celebrated them collectively. This improved morale and reinforced a culture of shared ownership. By this stage, team members demonstrated a clear understanding of interdependencies and began proactively sharing information, preventing bottlenecks before they occurred.

The Norming stage solidified cooperation and communication as standard practice, ensuring that information flow supported timely decision-making and aligned with project goals.

### Performing – Achieving High Efficiency and Synergy

As the project moved into the detailed design, permitting, and early procurement phases, the team reached the Performing stage, where coordination translated into tangible results.

Departments operated efficiently, with minimal oversight, because expectations and processes were well-established. As a PM and PMO, we shifted our focus from daily supervision to performance optimization, ensuring that resources, risks, and schedules were continuously monitored and adjusted for efficiency.

Key factors which we focused on during this phase are:

- Milestone tracking: Ensuring design completion aligns with CPUC approval timelines.

- Schedule integration: Linking construction readiness with vendor deliveries and environmental clearances.

- Continuous feedback: Gathering weekly input from functional leads to detect delays early and implement corrective actions.

- Empowerment: Allowing teams to make operational decisions within their domain, improving response time and accountability.

The Performing stage reflected the maturity of the project’s workforce characterized by autonomy, collaboration, and focus on common outcomes rather than departmental objectives.

### Adjourning – Lessons Learned and Continuous Improvement

As the Chino Hills project approached completion, the focus shifted toward knowledge capture, evaluation, and closure.
The PM and PMO organized structured lessons-learned workshops involving all departments to assess what worked effectively and where improvements can be made.

This will include:

- Documenting coordination challenges and solutions for future reference.

- Capturing data on cost efficiency, schedule control, and stakeholder satisfaction.

- Sharing technical innovations across other SCE transmission projects.

The PM also ensured proper resource release and team recognition, closing the project on a positive note to maintain morale for future assignments.
The final stage reinforced SCE’s organizational commitment to continuous improvement, ensuring that every project contributes to refining internal processes and strengthening interdepartmental collaboration.

Summary

The Chino Hills 500kV Transmission Line Project underscores the interconnection between Project Manager leadership and Project Management discipline. The Project Manager’s personal competencies, including leadership, decision-making, and ethical conduct, form the driving force behind project direction and stakeholder confidence. Simultaneously, structured Project Management processes including risk control, team development, and change management provide the stability and oversight necessary for consistent performance.

Together, a unified system was created that ensured coordination, compliance, and efficiency throughout the project lifecycle. The integration of human leadership and systematic management enabled the Chino Hills project to progress steadily toward its objectives, establishing a strong foundation for the Project.

# 9. Technology Challenge and Schedule Opportunity

The project management team ran into three unexpected situations, two challenges and a usable opportunity. The first challenge was deciding whether to keep building overhead or push the transmission lines underground. This required balancing schedule uncertainty and constructability against community and environmental concerns. The second challenge was unexpected failure of the final deliverable during energization testing. On the opposite end of the spectrum, the opportunity faced became apparent once the network diagram was live. The advantage of this opportunity was a more straightforward, shorter schedule and a slight reduction in total cost. The following section details how the project management team moved forward with each of these situations.

9.1 Challenges we faced — and how we handled them

While building, the biggest call was choosing whether to route the transmission lines overhead vs. underground. Underground would ease visuals and smooth relations with the residents of Chino Hills, but at 500 kV it would require first-of-their-kind duct banks, joint bays, thermal backfill, long splicing/testing, and extra permits— all taking more time and at greater cost risk.

The decision was made to push forward with overhead lines with the knowledge that this would have repercussions that needed to be mitigated. To ensure the installation would go smoothly, the project management team scheduled biological, geological, and regulatory surveys before installation, used dust/noise controls, kept environmental monitors on site, and set clear work windows. The project management team also kept a steady cadence with CPUC and the City of Chino Hills, requiring any requirements changes stemming from this challenge went through change control, so schedule and costs stayed predictable.

At the end of the project during energization testing, the electrical and wiring diagrams did not fully align with actual substation conditions. This created a hazard for both the installation process and future maintenance operations. As failure of the electrical diagrams could jeopardize acceptance of delivery of the transmission lines, the project management team quickly began performing a strategic recovery to keep the project on track.

The test technician was instructed to redline (mark changes to the original in red pencil) the substation drawings with the necessary revisions. The original design teams were then called back from their new projects to ensure accurate documentation was created from these redlined drawings. Once the drawings were up to date and ready for use, the final delivery could take place with only a minor delay.

9.2 Opportunity we used — targeted crashing

Once the network diagram was created and set, an opportunity was identified to crash multiple critical activities. Only tasks that were on the critical path were accelerated, and the schedule was reevaluated after each move. Through crashing five work packages—Project Charter, Scope of Work, Route Alignment, Cable drum delivery & setup, and As-built documentation—the total duration was cut from 2,191 days to 2,142 days (49 days saved). Direct costs rose about $51,000 but indirect costs fell by $58,800, resulting in a decrease in a net change in costs of $7,800.

Overall, handling the overhead/underground challenge swiftly, strategically recovering from the discovery of inaccurate drawings late in the project, and utilizing targeted crashing meant the project finished earlier, cost slightly less in total, and confidence in the project was strengthened with regulators, the city, and residents.

# 10. Status Reports

Status reports for the project were a way for project managers and stakeholders to keep abreast of progress and developments in the project. For this particular project, status reports were created and sent out on the first day of every month.

A sample status report has been included below (Fig. 6). The following section instead contains a broad overview of the information contained within all status reports created for this project.

Information included in Status Reports

- Project Name

- Date of Report

- Brief Project Description

- Earned Value Data section

- Status summary

- Explanations

- Major changes since last report

- Total cost of approved changes

- Projected Cost at Completion

- Projected Completion Date

- Current Risks

The data for each status report was gathered using communication methods outlined in phase 1, creating a trickle-up flow of formation to the project manager. In this way, the progress of each work package and costs were measured and tracked to most accurately measure Earned Value (EV) during each period.

# 11. Performance Metrics and Indexes

The data for this section can be found in Fig. 7.

Briefly mentioned above is the Earned Value Data section of the status report. This section of the status reports utilized Earned Value (EV) data gathered from the process mentioned above, Planned Value (PV) gathered from the Time Phased Budget, and actual costs (AC) gathered from accounting software to estimate how well the project was performing on cost and schedule. By analyzing this data, project managers quantified the status of the project at the end of each period in terms of schedule and budget over and underruns, as well as projected the data into the future to estimate final project totals for those same categories.

We can compute Cost Variance (CV) from the difference between the Earned value and the Actual Cost and the Schedule Variance from the difference between the Earned Value and the Planned Value. These are mainly used in the status reports to see exactly how far from the expected values the project is on schedule and at the cost.

In order to quantify the project as over or under the budget or schedule at the time each status report captures, two metrics were utilized: the Cost Performance Index (CPI) - a measure of how much work has been done per dollar spent, and the Scheduling Performance Index (SPI) - a measure of how much work has been done per dollar expected to be spent by that point.

When utilizing these metrics, it is important to note that early gains in EV compared to PV or AC can be misleading and should be treated with caution. Budget or schedule overruns can have a number of causes, including but not limited to cost cutting and rushed execution (which can have long term negative effects that do not manifest until later on in the project lifecycle) or simply enthusiasm brought on by the start of a new project that can fade over time.

That said, this data can be expanded further by projecting current cost totals into the future to see whether the project is on track to finish with favorable spending compared to the budget. Estimated Cost to Complete Work (ETC) works by finding the remaining EV left to gain and dividing it by the CPI. The Actual Cost at Completion (EAC) is an extension of this that adds the AC to the ETC. Finally, the expected cost is subtracted from the EAC to get the expected Cost Variance at Completion (VAC).

All of these metrics are important in understanding whether the project is on track to meet targets or whether strategic recovery is needed to bring the project back in line with projections and are included within the Status Reports.

# 12. Project Closure

Due to the multi-project landscape of SCE and the highly regulated nature of the industry in which it operates, project closure for the Chino Hills section of the Tehachapi Project was a daunting task.

Complicating matters is the highly regulated nature of the electric utility industry. Each and every project SCE completes must follow strict regulations in order to comply with laws and ordinances, all of which affect final delivery needs and activities.

Nevertheless, the project manager oversaw the smooth transition of employees and a successful handoff of project deliverables to the customer (in this case, another division of SCE) at the end of the Chino Hills Transmission line project.

## 12.1 Project closure Activities

For the Chino Hills portion of the Tehachapi Renewable Transmission project, major project closure activities included the following:

- Final tests and certification (analogous to delivery acceptance)

- Energizing (analogous to delivery)

- Performing a post project audit and team evaluation

- Shutting down and releasing project resources and team members

- Closing accounts

- Creating the final report

## 12.2 Delivery Acceptance and Delivery

The work breakdown sheet from Phase 1 shows that the end of the project consists of work packages for final testing, certification, and energization tasks. Together, these packages accounted for the project closure tasks of delivery acceptance and delivery.

The tests used by SCE in the closing phase of the project were designed in the development phase of the project to ensure that the final transmission lines would meet or surpass the requirements laid out in the project scope. Some tests were also mandated by regulatory bodies to ensure compliance with laws and regulations regulating the utility industry. Others were pulled from previous projects. In the case that a novel requirement had been agreed upon that could not be tested using previously developed methods, the engineering team in charge of design developed tests prior to closure that would be used to validate the final deliverable.

These tests were presented and agreed upon by all parties involved in the project in a meeting held between all stakeholders. At the end of the project, certification of the transmission lines was awarded after successful validation of regulatory requirements through these tests.

Once certification was confirmed and the transmission lines were connected to their neighboring segments, final energization was initiated. Due to the nature of the project, this task was considered the final delivery of the project.

## 12.3 Performing a Post-Project Audit and Team Evaluation

As the project began to wind down, the Project Management team began to schedule performance reviews with each team member of the project. Each performance review was a two-part process:

First, each employee was asked for their opinions as to their own performance, potential improvements, and what the company could do better or change to improve efficiency and working conditions. Following that, their manager or project manager conducting the interview reciprocated with their performance review on the employee. A third party was the room for all performance reviews, both to take notes, and to conduct the review when necessary.

Concurrently, the project management team began a post-project audit. In this audit, the team answered specific questions, including:

- What lessons were learned during the project?

- What were successful and unsuccessful ways risks and issues were dealt with?

- What were the main causes for the project going over/under budget/schedule?

- In what ways could the team perform better?

- In what ways did team dynamics affect project outcomes?

The post-project audit and performance reviews were utilized to inform future decisions about team placement and will continue to provide valuable feedback on how to better manage future projects within SCE.

## 12.4 Shutting down the project

Many different teams and resources were pulled for the Chino Hills section of the Tehachapi Renewable Energy Transmission Project, many of which were utilized and shared in multiple sections of the overarching program. At the closure of the Chino Hills section, the main challenge was ensuring that the teams and resources remaining on the project were reassigned and utilized quickly for other projects in the SCE project portfolio.

Resources commonly shared among projects are in high demand at SCE. This made the task of reassigning them easier, as the demand was already apparent. The main task to be tackled by the project management team was to ensure the resources were prepared to be moved offsite in time for their next assignments.

For team members, the project management team needed to decide how to reassign team members or entire sub teams shortly after the close of the Chino Hills section project. Most teams were fully transitioned to their new assignments within days of project closure.

## 12.5 Closing Accounts

Once the project came to a close, it was time to close accounts for the project. Using expense tracking software, all actual costs associated with the project had been tracked. Using this information, all vendors and employees were paid, and backup documentation was kept orderly for future audits. Only a few minor payment discrepancies with vendors were discovered and handled regarding late payment charges that had not been entered into SCE’s books.

## 12.6 Final Report

Once the project was delivered, the project management team needed to complete a post-project audit. Ideally, the process of compiling information for the audit began shortly before the actual end of the project to ensure team members being reassigned are included.

Similar metrics to the status reports would be analyzed in the final report to find out whether final goals of cost and time were met. As SCE found completes variations of this transmission line project regularly (though most are at a smaller scale), the results are expected to be used to inform SCE in similar future projects.

Equally important to individual project performance is an examination of the project within the broader SCE portfolio. Questions to be answered included: “Did this project enable SCE to provide better service in its target area?” “Did this project deliver on the expected strategic benefits of connecting the Inland Empire with the LA power grid?” “What lessons can be learned from this project to ensure we do not repeat mistakes made during this project?” “Would we prioritize this kind of project again and why?”

The final report was made available to SCE’s project management teams through the SCE project portfolio and tracking database.

# 13. Where is SCE on the Project Management Maturity Model

The project closure phase marks the formal completion of the project and ensures that all work has been finalized according to scope, quality, and compliance standards. In the case of this project, two essential closure activities were implemented that showcase SCE’s standards practices. The first was the as-built submissions (7.2.1). During system testing, the electrical and wiring diagrams did not fully align with actual substation conditions, prompting the test technician to redline the substation drawings with the necessary revisions. These updated drawings were then submitted to the responsible engineer to ensure accurate documentation for future maintenance and operations. The second key activity was the preparation and submission of the lessons learned report (7.2.2), which was formally entered into SCE’s lessons learned repository to help guide future projects and promote continuous improvement.

As part of SCE’s well-established project management framework, the process of closing and in-servicing a new transmission line followed standard organizational procedures. This project reflects Level 4 of the Project Management Maturity Model, as SCE maintains a mature Management of Project Office (MPO) department and practices portfolio project management to ensure strategic alignment across initiatives. Finally, performance appraisals were conducted by departmental managers to evaluate team effectiveness, recognize contributions, and identify areas for development. These steps demonstrate SCE’s commitment to structured project governance, organizational learning, and long-term operational excellence.

# 14. Conclusion and Lessons Learned

## By Project -

The Chino Hills 500kV section of the Tehachapi Reliability Transmission Project (TRTP) represents an immense effort to modernize regional electric power capacity and operational efficiency through careful planning, coordination and execution. Throughout the project, the integration of technical analysis, risk assessment, and optimizing the schedule ensured that design and construction phases aligned with SCE’s safety standards and regulatory requirements. The project demonstrated how early stakeholder engagement, consistent communication, and a balanced matrix organizational structure contributed to timely decision-making and reduced uncertainty during implementation.

In reflection, a complex project of this magnitude demonstrated the critical role of collaboration, adaptability, and authentic leadership in achieving project success.  The lessons learned from this project will inform future transmission infrastructure projects, highlighting the value of transparent communication, rigorous planning, and team synergy in overcoming complexity and most of all ensuring long-term reliability for the electrical grid.  This is another example of SCE leading through innovation, turning complex challenges into opportunities to modernize the grid, strengthen reliability, and set new standards for other utilities to follow on project delivery. The Chino Hills 500 kV section stands as a model of how commitment, foresight, and innovation can power a more resilient energy future.

## By EMT 6360 Project Group -

In doing this project, our group learned a number of technical, leadership, and team-based lessons. These include how to implement time and cost projections in a large-scale project, the importance of pre-planning and delegating, the importance of holding people accountable, how to use incremental check-ins to promote consensus among the group, and the importance of keeping an open mind during group discussions.

Each team member’s style also greatly contributed to the success of the final project. Roberto was found to be a great listener and resource for the project as he had a great depth of knowledge on the subject matter. Pearl’s detail-oriented nature ensured that we were all on the same page when it came to concepts involved in the project and making sure items were completed correctly. Brian contributed practical, real-world insight into how projects operate beyond classrooms. His approach emphasized structure, accountability, and results, helping the team stay on track.

The team norms that contributed to the success of the project were regular check-ins, early division of labor, making sure we get responsibilities in writing, and making volunteering for tasks the norm for task assignment. By doing these things, the team was able to work together harmoniously (after the storming phase of course) to complete both phases of the project.

Finally, the organizational lessons the group learned from challenges faced in the project were that it is extremely important to ensure the vision for the project is clear with all team members from the start, that ensuring team members find time to work together in person or via Zoom is challenging but rewarding, and that it is extremely important to utilize a single shared repository for project information so that every team member can keep track of both their and the rest of the group’s progress in real time.

# Appendix

## Fig. 1 - Resources and Estimated Costs per Work Package

## Fig. 2 - Loading Schedule

## Fig.3 - Time Phased Budget

## Fig. 4 - Project Network Diagram

Fig. 5 - Cost/Schedule Crashing

| Total Indirect cost | $1,104,000.00 |
| --- | --- |
| Saving per Unit Reduced | $1,200.00 |
| Duration | 2191 |
| Total Direct Cost | $15,315,000.00 |
| Actual cost | $16,419,000.00 |
| New Actual cost | $16,411,200.00 |
| New Duration | 2142 |

| Activity | Crash Cost | Maximum Crash Time | Normal Time | Normal Cost | Indirect Cost |
| --- | --- | --- | --- | --- | --- |
| Project charter | $2,000.00 | 2 | 10 | $10,000.00 | $2,000.00 |
| Scope of Work | $2,000.00 | 4 | 20 | $10,000.00 | $2,000.00 |
| Regulatory Permits | $15,000.00 | 5 | 20 | $50,000.00 | $10,000.00 |
| Environmental Compliance | $22,500.00 | 5 | 21 | $75,000.00 | $10,000.00 |
| Route alignment | $10,000.00 | 10 | 42 | $30,000.00 | $10,000.00 |
| Seismic design & load studies | $10,000.00 | 10 | 42 | $30,000.00 | $10,000.00 |
| Footing design | $70,000.00 | 12 | 48 | $200,000.00 | $50,000.00 |
| Tower structure design | $100,000.00 | 12 | 48 | $300,000.00 | $75,000.00 |
| Cable sizing & specification | $12,000.00 | 7 | 28 | $40,000.00 | $10,000.00 |
| Grounding system design | $45,000.00 | 12 | 48 | $150,000.00 | $50,000.00 |
| Relay/protection coordination | $30,000.00 | 10 | 42 | $120,000.00 | $50,000.00 |
| 500kV cable procurement | $1,100,000.00 | 35 | 100 | $3,000,000.00 | $100,000.00 |
| Tower Structural Materials | $1,000,000.00 | 24 | 84 | $2,500,000.00 | $100,000.00 |
| Surveying & staking | $40,000.00 | 16 | 56 | $150,000.00 | $50,000.00 |
| Clearing & grading | $450,000.00 | 24 | 84 | $1,200,000.00 | $100,000.00 |
| Tower structure construction | $450,000.00 | 24 | 84 | $1,200,000.00 | $100,000.00 |
| Tower structure Assembly | $1,120,000.00 | 15 | 45 | $2,500,000.00 | $100,000.00 |
| Cable drum delivery & setup | $22,000.00 | 20 | 70 | $100,000.00 | $25,000.00 |
| Cable pulling operations | $1,120,000.00 | 40 | 105 | $2,500,000.00 | $100,000.00 |
| Cable Splicing | $240,000.00 | 20 | 70 | $600,000.00 | $75,000.00 |
| Cable Testing | $30,000.00 | 7 | 30 | $100,000.00 | $20,000.00 |
| Pre-energization checklist | $20,000.00 | 10 | 28 | $150,000.00 | $20,000.00 |
| Energization testing | $25,000.00 | 10 | 28 | $100,000.00 | $15,000.00 |
| As-built documentation | $15,000.00 | 13 | 28 | $150,000.00 | $10,000.00 |
| Lessons learned Report | $5,000.00 | 4 | 14 | $50,000.00 | $10,000.00 |

| Duration | 2191 | 2189 | 2185 | 2175 | 2155 | 2142 |
| --- | --- | --- | --- | --- | --- | --- |
| Activity |  | Project Charter | Scope of work | Route Alignment | Cable drum delivery & setup | As-built documentation |
| Actual Cost | $16,419,000.00 | $16,418,600.00 | $16,415,800.00 | $16,413,800.00 | $16,411,800.00 | $16,411,200.00 |
| Direct Cost | $15,315,000.00 | $15,317,000.00 | $15,319,000.00 | $15,329,000.00 | $15,351,000.00 | $15,366,000.00 |
| Indirect Cost | $1,104,000.00 | $1,101,600.00 | $1,096,800.00 | $1,084,800.00 | $1,060,800.00 | $1,045,200.00 |

## Fig 6 – Sample Status Report

Project Name: Tehachapi Project – Chino Hills Section

Date of Report: 2025-10-01

Brief Project Description – The Project covers the design, installation, and energizing of two substations and 500 kV transmission lines connecting them. These will be constructed in an existing energy corridor through the city of Chino Hills.

Earned Value Data

| Task | % Complete | EV | AC | PV | CV | SV |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 100 | 75 | 77 | 75 | -2 | 0 |
| 2.1 | 100 | 50 | 57 | 50 | -7 | 0 |
| 3.1.1 | 100 | 30 | 42 | 30 | -12 | 0 |
| 3.1.2 | 60 | 18 | 23 | 21 | -5 | -3 |
| 3.2.1 | 40 | 80 | 82 | 108 | -2 | -28 |
| 3.3.3 | 95 | 114 | 115 | 117 | -1 | -3 |
| 3.3.2 | 35 | 52.5 | 61 | 85 | -8.5 | -32.5 |
| Totals |  | 434.5 | 472 | 501 | -37.5 | -66.5 |

| Period |  | EV | AC | PV |  | SPI | CPI | PCI-B |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | 14 | 15 | 15 |  | 0.93 | 0.93 | 0.001 |
| 2 |  | 45 | 50 | 52 |  | 0.87 | 0.90 | 0.003 |
| 3 |  | 112 | 129 | 130 |  | 0.86 | 0.87 | 0.007 |
| 4 |  | 281 | 306 | 308 |  | 0.91 | 0.92 | 0.018 |
| 5 |  | 434.5 | 472 | 501 |  | 0.87 | 0.92 | 0.028 |
| EACf | = | 16636.78 |  | VACf | = | -1321.78 |  |  |

Status summary

The project is currently projected to be overbudget by about $1.3 million at completion. As it stands now, we are also somewhat behind schedule, but well within our generous time buffer. The project management team are prepared to utilize opportunities to decrease the schedule and costs where possible, however the main concern continues to be satisfactory completion of all required deliverables.

Explanations

This past period saw the project finish numerous critical activities of the project, allowing downstream activities to be pushed forward. Great time and cost savings were found in work package 3.1.1, however these were negated by expensive technical issues discovered and worked through in work package 3.2.1. The rest of the project continues at the scheduled pace.

Major changes since last report

- Design changes in the footing design work package 3.1.1.

Total cost of approved changes

~$20,000

Projected Cost at Completion

$16,636,780

Projected Completion Date

August, 2028

Current Risks

- Further discovery of as yet unknown technical requirements

## Fig. 7 – Status Report Data and Performance Metrics (Including Graph)

| Status Report: Ending Month 1 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 90 | 9 | 10 | 10 | -1 | -1 |
| 1.2 | 50 | 5 | 5 | 5 | 0 | 0 |
| Totals |  | 14 | 15 | 15 | -1 | -1 |
| Status Report: Ending Month 2 |  |  |  |  |  |  |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 40 | 30 | 35 | 37 | -5 | -7 |
| Totals |  | 45 | 50 | 52 | -5 | -7 |
| Status Report: Ending Month 3 |  |  |  |  |  |  |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 80 | 60 | 73 | 75 | -13 | -15 |
| 2.1 | 50 | 25 | 27 | 25 | -2 | 0 |
| 3.1.1 | 40 | 12 | 14 | 15 | -2 | -3 |
| Totals |  | 112 | 129 | 130 | -17 | -18 |
| Status Report: Ending Month 4 |  |  |  |  |  |  |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 100 | 75 | 77 | 75 | -2 | 0 |
| 2.1 | 90 | 45 | 53 | 50 | -8 | -5 |
| 3.1.1 | 60 | 18 | 29 | 30 | -11 | -12 |
| 3.1.2 | 50 | 15 | 15 | 15 | 0 | 0 |
| 3.2.1 | 25 | 50 | 53 | 53 | -3 | -3 |
| 3.3.3 | 40 | 48 | 50 | 51 | -2 | -3 |
| 3.3.2 | 10 | 15 | 14 | 19 | 1 | -4 |
| Totals |  | 281 | 306 | 308 | -25 | -27 |
| Status Report: Ending Month 5 |  |  |  |  |  |  |
| Task | % Complete | EV | AC | PV | CV | SV |
| 1.1 | 100 | 10 | 10 | 10 | 0 | 0 |
| 1.2 | 100 | 5 | 5 | 5 | 0 | 0 |
| 2.2 | 100 | 75 | 77 | 75 | -2 | 0 |
| 2.1 | 100 | 50 | 57 | 50 | -7 | 0 |
| 3.1.1 | 100 | 30 | 42 | 30 | -12 | 0 |
| 3.1.2 | 60 | 18 | 23 | 21 | -5 | -3 |
| 3.2.1 | 40 | 80 | 82 | 108 | -2 | -28 |
| 3.3.3 | 95 | 114 | 115 | 117 | -1 | -3 |
| 3.3.2 | 35 | 52.5 | 61 | 85 | -8.5 | -32.5 |
| Totals |  | 434.5 | 472 | 501 | -37.5 | -66.5 |

| Performance Indexes Summary |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Period |  | EV | AC | PV |  | SPI | CPI | PCI-B |
| 1 |  | 14 | 15 | 15 |  | 0.93 | 0.93 | 0.001 |
| 2 |  | 45 | 50 | 52 |  | 0.87 | 0.90 | 0.003 |
| 3 |  | 112 | 129 | 130 |  | 0.86 | 0.87 | 0.007 |
| 4 |  | 281 | 306 | 308 |  | 0.91 | 0.92 | 0.018 |
| 5 |  | 434.5 | 472 | 501 |  | 0.87 | 0.92 | 0.028 |
| EACf | = | 16636.78 |  | VACf | = | -1321.78 |  |  |