## Sheet1
Criteria | Priority | Description | Criteria | Priority | Description
Time | Constrain | Must meet CPUC’s 6-year deadline tied to California’s 33% renewable goal; delays not acceptable. | Proformance | Constrain | Must meet 500kV technical, regulatory, and safety requirements.
Scope | Enhance | Undergrounding scope enhances stakeholder trust, safety, aesthetics, and regulatory alignment. | Cost | Enhance | Budget efficiency prioritized.While capped at $50M, flexibility is allowed with approvals from Exceutives.
Cost | Accept | Budget flexibility limited; while capped at $50M, overruns may be accepted with executive/CPUC approval. | Time | Accept | Flexible within 6-year CPUC deadline tied to California’s 33% renewable goal, supported by a 6-month buffer.