## Risk Analysis
Risk ID | Risk Description | Cause/Source | Probability (H/M/L or 1-3) | Impact (H/M/L or 1-3) | Priority (P×I) | Owner | Analysis | Monitoring | Response Strategy (Avoid/Mitigate/Transfer/Accept/Escalate) | Strategy | Time Buffer | Contingency Funds
R1 | Public opposition or protests | Community concerns over safety, EMF exposure, noise | 3 | 3 | 9 | Project Manger/Community Relations | High likelihood of community pushback; could cause major schedule delays. | Weekly - Track community complaints, monitor media & social platforms | Mitigate and Escalate | Escalate to Senior Management / Local Government -Resolve disputes where possible and maintain project continuity if community pressure escalates | 3 months
R2 | Delay in CPUC approval | Delay in review, missing documentation | 3 | 2 | 6 | Regulatory Affairs | CPUC delays are common; impacts project start date. | Bi-Weekly - Review permit approval status, direct CPUC updates | Mitigate | Submit complete docs early, follow up regularly, monitor CPUC status | 2 months | 200000
R3 | Environmental non-compliance | Dust, noise, wildlife disruption and potential hazardous material spillages. | 2 | 2 | 4 | Regulatory Affairs | Regulatory fines possible, but impact contained if monitored. | Weekly - Site inspections, environmental audit reports | Mitigate | Regular site inspections, environmental audits, dust/noise control, wildlife monitoring |  | 400000
R4 | Vendor supply chain delay | vendor qualification delays, Long lead times for 500kV cables & tower materials | 2 | 3 | 6 | Procurment Lead | Any delay in getting materials to the work site delays the project completion date | Weekly - Vendor delivery reports, milestone tracking | Mitigate / Transfer | Track vendor milestones, maintain multiple suppliers, order long-lead items early. Tranfer to Vendors (via contractual obligations with penalties) | 3 months
R5 | Cable splicing or testing failure | Design Errors, Workmanship issue (Flaws in the engineering of the system, such as incorrectly sized equipment, insufficient structural capacity for towers, or incomplete drawings) | 2 | 3 | 6 | Engineering lead/Procurement lead | Unlikely, potential to be highly disruptive if not caught during testing | Per Test Cycle - Quality control tests, engineering sign-offs | Mitigate & Accept | Quality control tests, design peer review, backup components ready. Be prepared for Minor failures absorbed within testing schedule | 1 month | 2000000
R6 | Construction complexity & unforeseen ground issues | Seismic faults, soil instability, access challenges | 2 | 3 | 6 | Construction Lead | Soil instability and seismic risks significant in Chino Hills. | Daily Before starting the construction and weekly once the construction is started | Escalate | Senior Project Manager / Engineering Director - Geotechnical surveys, adjust construction methods, worker training | 1 month | 4000000
R7 | Worker injury or accident | High-voltage handling, heavy equipment | 2 | 2 | 4 | Construction Lead | High safety risks involved with working with high voltage cables and heavy machinery; accidents could halt work temporarily. | Daily - Safety incident reports | Mitigate/Transfer | Minor incidents can occur, Enforce PPE, safety drills, daily safety reporting, accident insurance |  | 2000000
R8 | Budget overrun | Underestimated costs, scope creep | 2 | 2 | 4 | Project Manager | Contingency planning required; scope creep is a concern. | Monthly - Cost variance reports, earned value tracking | Escalate /Tranfer | Senior Management - Track costs, control scope creep, review contracts. Transfer financial risk to contractors through fixed rate contracts and the government through budget increase clauses for mutually agreed changes in project requirements or expansions of scope. |  | Management Funds
R9 | Ineffective stakeholder communication | Misalignment between CPUC, city, contractors | 3 | 3 | 9 | Project Manager | Misalignment can cause rework and delays. | Bi-weekly - Meeting minutes, communication dashboard | Escalate | Escalate to Senior management to keep the project completion on track | 1 month | 500000
R10 | Extreme weather impacts | Heavy rain, heatwaves | 3 | 1 | 3 | Construction Lead | Weather events are likely but can be planned for. | Seasonal - Weather alerts, contingency planning checks | Mitigate | Contingency plans for weather, flexible schedule, monitor alerts | 5 months | 1500000
R11 | Labor strikes or shortage | Union disputes, lack of skilled cable jointers | 2 | 2 | 4 | Procurement Lead | Workforce availability risk due to union disputes. | Monthly - Based on union negotiations status | Transfer | Maintain buffer workforce, cross-train staff, negotiate labor agreements | 2 months | 2000000
R12 | Seismic Activity | Earthquakes occur in the area frequently. Earthquakes of sufficient size to cause damage or risk to the project however, are rare. | 1 | 3 | 3 | Accept | Seismic events are unpredictable but rare. | Weekly - Check recent seismic activity for upticks in frequency and intensity as these could indicate increased likelihood for a major seismic event. | Accept | Keep all staff aware of safety protocals necessary for major seismic events, prepare emergency preparedness plans for each work site along the route |  | 1000000
[11 empty] | Management Funds | 18200000
| Probability / Impact | Low | Medium | High
| Unlikely |  |  | R12
| Moderate |  | R3,R7,R8,R11 | R4,R5,R6
| Very Likely | R10 | R2 | R1,R9